Sustainability of the IDB data exchange

--------------------------------------------------------------------------------------------

Technical report on the sustainability of the IDB data exchange at EU level under the new health information infrastructure

This report is a deliverable of the BRIDGE-Health project, which aims to prepare the basis for a comprehensive EU health information system and which receives co-funding from the EU Health Programme.

D 9.2: Report on the sustainability of IDB exchange at EU level under the new Health Information Infrastructure 2018+.

Authors:

Rupert Kisser1, Wim Rogmans2, Ronan A Lyons3,4

1Eurosafe, Austria; 2EuroSafe, The Netherlands; 3Farr Institute Swansea University, Medical School, UK; 4Public Health Wales NHS Trust, UK.

Published by European Association for Injury Prevention and Safety Promotion (EuroSafe)

www.eurosafe.eu.com.

12 November 2017

Table of contents

- Introduction and background								3

- Purpose of the report and its target groups						4

- IDB Implementation score cards and other Information sources			5

- Initial status 2015: Inadequacies of national implementations				9

- Improvement plans 2015-2017								12

- Achievements and set-backs: Status of implementations (2017)			14

- Efforts to improve geo-coverage (2017)						16

- Status of the EU web-gates (2017)							19

- Perspective for the future								21

- References										25

Annex 1: Table “IDB Implementation scores by country and year” 2015 and 2017		27

Annex 2: IDB implementation score card reports 2015 and 2017				28

Annex 3: IDB implementation reports (from EuroSafe Alert)				            161

Annex 4: List of proposed improvements of EU IDB web-gate				            206

- Introduction and background

The European IDB system processes national data on attendances of emergency departments of hospitals for diagnosed acute injuries. It exists since the early eighties and was formally focussed on product related injuries at home and during leisure activities. After 2005 the scope was expanded to all injuries, including workplace and road traffic accidents, violence and deliberate self-harm. After 2010 the focus shifted from details of external causes to the production of internationally comparable national indicators for the health burden of injuries. As a consequence, more attention was paid to the improvement and harmonization of methods, e.g. coding, sampling and estimation.

The methodology is comprehensively laid down in the IDB Operating Manual [1]. The Manual addresses all aspects which are important for a deriving valid statistic. See as reference e.g. the Euro SDMX Metadata Structure (ESM) as used by Eurostat [2].

In 2013, the ECHIM-project [3] recommended to use IDB data for estimating the European health indicators on injuries, particularly ECHI-29b (Home, Leisure and School Accidents: Register based injuries) and eventually also ECHI-30b (Road Traffic Accidents: Register based injuries) and ECHI-31 (Work-place injuries), which are listed in the ECHI-shortlist of 88 indicators, which are considered as desired and feasible for all EU member states.

The previous EU-project JAMIE (2012-2014) [4] harmonized the IDB methodology for this purpose (see the IDB Operating Manual [1]) and promoted the implementation of the IDB data collection in European countries. 26 countries participated in this project, where of 21 countries could produce estimated rates as ECHI-29b (see the report on “Injuries in the EU” [7]).

The current BRIDGE-Health project’s work-package 9 (2015-2017) aimed to maintain the system, by providing the necessary central services for IDB data supplying countries, to increase the number of participating countries and to prepare for the integration of injury data into a future EU Health information system [6].

Eligible for participation are 36 European countries, i.e. 28 EU member states, 3 EEA-countries (Iceland, Liechtenstein, Norway) and 5 candidate countries (Albania, Macedonia, Montenegro, Serbia, Turkey). Between 2012-2017, 26 countries participated actively (for details see also the report on IDB data flow [7].

Since the start of the European injury surveillance system in the eighties, the data were collected and hosted centrally by competent Commission services. In 2002, a central data base has been established, which gives publicly access to the data through a web-gate providing basic tools for analysing the data and comparing rates for varying sub-groups – the EU IDB database [8], hosted by DG SANTE. Very recently it has been decided to publish the IDB based indicator ECHI-29b also through the ECHI-web-gate [9], for as many countries and years as possible, for 2009 and following years.

Currently, the entire complex of EU health information is under revision. It is the intention to combine all EC health information activities into a new European Research Infrastructure [10]; activities will be prioritized by actual data availability and policy information needs. This report should help with such decisions regarding injury data and health indicators on injuries, i.e. a health problem that accounts for more than 8% of all days of hospital care recorded in Europe [5].

- Purpose of this report and its target groups

This report shall inform decision makers about

- Scope and quality of current national IDB implementations at the begin of the BRIDGE-project (2015);

- Scope and quality at the end of the BRIDGE-project (2017), improvements and set-backs, in order to monitor the development of surveillance practice in countries;

- State of play in countries without IDB injury surveillance in assess the opportunities for new countries in developing their systems;

- Sustainability of the system under a new EU health information system.

Main target groups are:

- Decision makers in the areas of health information in member states (e.g. national public health institutes, ministries of health, national bodies dealing with health data, members of the EGHI-group, researcher in the areas of public health and injury epidemiology)

- Decision makers at EU-level (e.g. concerned EU Commission services as in DG Health and Food Safety, DG Justice and Consumers, Eurostat, Joint Research Centre, DG Research) and the EP, particularly members of concerned committees (e.g. Internal Market and Consumer Protection, Environment, Public Health and Food Safety).

The report has been produced in the framework of the following project:

- BRIDGE-Health project [6], Work package 9 “Platform for injury surveillance”

- It is mainly related to Task 2 “Expand IDB to remaining countries, maintain the current implementations and expand the scope to all injuries” and Task 3 “Maintain and further enhance the quality of implementations, monitor surveillance practice and assist countries in developing their systems”

- Deliverable D9.2b “Technical report on the sustainability of the IDB exchange at EU level under the new Health Information Infrastructure 2018+.”

- IDB Implementation score cards and other Information sources

For the assessment and monitoring of quality and sustainability of the IDB data collection, mainly three sources of information have been taken into account:

- National IDB implementation score card reports (Annex 2).

- Presentations of data suppliers at the three IDB-network-meetings, which took place during the BRIDGE-project (September 2015 in Lisbon, November 2016 in Vienna, and September 2017 in Amsterdam).

- National IDB implementation reports, which have been published in the EuroSafe-Alert newsletter. These reports are also annexed to this volume (Annex 4).

For monitoring the quality of national implementations of the IDB system a questionnaire (“IDB implementation score card”) has already been developed already during the previous JAMIE project [11]. It consists of 26 questions which cover four major aspects of the EU IDB data exchange:

- Quality of the participation in the EU IDB-data exchange (4 questions, max. 8 points)

- Quality of factually delivered data (7 questions, max 14 points)

- Quality of the national injury surveillance system (10 questions, max. 20 points)

- Sustainability of the national injury surveillance system (5 questions, max. 10 points)

The items cover qualities which are considered as important for quality and sustainability of the system and for which the fulfilment cannot be taken as granted.

For each question up to 2 points could be reached: Two points are assigned for a full compliance with the guidelines as outlined in the IDB Operating Manual; one point is assigned, when requirements are only met partly, and zero points, if a national implementation fails in this respect.

To a large extent, the four aspects are independent from each other: Network-members can be interested in the exchange of experiences even without operating an own data collection system, and countries with a functioning system may not be interested in participating in the EU data exchange. A functioning national system does not necessarily mean that data are actually delivered in time to the Commission and collaboration in the past does not guarantee its continuation in the future. Although when no data have been provided in the past, there could be solid future perspective. However, delivery of data is not possible without having a system in place, which fulfils at least the minimum quality criteria.

Individual items are not independent from each other, and responses to these items do not solely depend on one underlying dimension. As qualitatively different systems may get the same scores, the scores are no unambiguous measurements. Scores are just rough indicators which reflect differences between target and actual state, between different years or countries, and additional qualitative analysis is necessary to get the full picture. Table 1 contains items and their ratings of the “score card”.

| Table 1: Items of the “IDB implementation Score Card” and their codes (2017 version) |  |  |  |  |
| --- | --- | --- | --- | --- |
| A. Participation in EU-exchange |  |  |  |  |
| Question | 0 point answer | 1 point answer | 2 points answer | Rationale |
| - Membership as observer or full member NDA-network | not yet | just since start of BRIDGE-HEALTH (2015) | already before BRIDGE-HEALTH | Duration of membership is a strong indicator for the future |
| - Participation level in past five years | 2 or less of the eight meetings attended | 3-4 of the meetings attended | at least 5 meetings attended | Presence is essential, because meetings are also training events |
| - Government endorsement perspective for NDA-participation | No or only weak support | only for duration of BRIDGE-HEALTH | for longer term endorsement | Governmental organizations are considered as most reliable partners |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls | after 1 or 2 reminders | within deadline | Responsiveness is an indicator for reliability |
| B. Data delivery |  |  |  |  |
| Question | 0 point answer | 1 point answer | 2 points answer | Rationale |
| - Data delivered in past five years (2012-2016) | none | data delivered for just one year | data delivered for two or more years | Duration of data delivery is a strong indicator for the future |
| - MDS data 2016 delivered | Not available | Not yet but expected | complete and in time | Indicates timeliness of delivery |
| - Accuracy of coding (most current delivery) | more than 40% unknown | between 10% and 40% unknown | less than 10% unknown | Indicates striving for improving data quality |
| - Incidence rate | Not available | Only on paper or not for last delivery | Reference population file for 2016 | Core deliverable of IDB |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available | not consistent or unclear | Consistent | Indicates striving for high quality estimates |
| - Scope of data collection | Two or more “warning flags” | Just one “warning flag” | No “warning flag” | Indicates striving for high quality estimates |
| - FDS sample 2016 | Not available | Not yet but expected | Complete and in time | Indicates striving for high quality estimates |
| C. Current system in place |  |  |  |  |
| Question | 0 point answer | 1 point answer | 2 points answer | Rationale |
| - Data collection ongoing | no data & no plan to (re)start | no data but restart planned / data delivery uncertain | Collected & delivery certain | Ongoing data collection is best forecast for data delivery next year |
| - Age groups | not covering the full age-span | All ages in most of the hospitals | all ages in all hospitals | Indicates compliance with basic requirements |
| - Injury categories | less than ECHI-29 | At least home, leisure & school | all injuries | Indicates compliance with basic requirements |
| - Outpatients | none or strongly biased toward HD | biased toward HD but corrected for IR | All HDs + all EDs | Indicates compliance with basic requirements |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing | just one missing | all codes implemented | Indicates compliance with basic requirements |
| - Incidence rates | IR not available | only crude rate or based on catchment | standardized for age and sex | Core deliverable of IDB |
| - Geo-coverage | IR not available | Valid only for a region | Valid at national level | Indicates compliance with basic requirements |
| - Sampling of hospitals | Just by availability of hospitals | rational sampling but no validation check | Validated sample | Indicates compliance with basic requirements |
| - Hospital sample size | none or below advised minimum | Hardly above advised minimum (Table 4.1) | well above advised minimum (Table 4.1) | Indicates compliance with basic requirements |
| - FDS data | none | Sample below minimum expected (<3000) | Sample above minimum expected (3000+) | Indicates use of data for prevention |
| D. Prospects for 2018+ |  |  |  |  |
| Question | 0 point answer | 1 point answer | 2 points answer | Rationale |
| - Will the MDS data collection continue in 2018? | no | Not secured yet | yes | Strongest indicator for next two years |
| - Improvement or maintenance plan in place for next years? | None or just draft | in consultation | Yes or no substantial improvements necessary | Indicates willingness to strive for improvement |
| - Legal basis for MDS data collection? | No plans | Ongoing substantial discussion | In place or very likely | Strongest basis for sustainable data collection |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced | Scarce but stay the same | Sufficient or will increase | Indicates eventual changes in the future |
| - Interest to participate in future EU injury information projects? | no | Yes, but depending on availability of internal resources | Yes, we remain strongly interested | Indicates willingness to participate in EU exchange |

During the BRIDGE-Health project two ‘snap-shot’ were carried out:

- The “Baseline BRIDGE Score Card” depicts the status at the beginning of the project (May 2015) and deals with the data delivered up to 2014 and with the perspectives for the time of the project, i.e. 2016-2017.

- The “Final BRIDGE Score Card” reflects the status at the end of the project (October 2017) and deals with the data delivered up to 2016 and with the perspectives for the forthcoming years 2018+.

At the end of the previous JAMIE-project, “final JAMIE Score Cards” depicted the status of August 2014. These reports have been explicitly agreed with the individual national IDB data administrators [12]. After the start of the BRIDGE-Health-project (May 2015), the template was slightly revised in order to put a stronger focus on the future perspectives of national IDB implementations under an eventual new European health information infrastructure. A few additional questions were taken on board and a few others, less relevant ones were dropped. The four groups of items, the number of 26 questions and the maximum of 52 points stayed the same. The final JAMIE score cards of 2014 got “decanted” into the updated template, and amended with information available through most recently delivered data. This resulted in the “Baseline BRIDGE Score Cards”, which show the status of 2015.

The “Final BRIDGE Score Cards” of 2017 got explicitly agreed with each data supplier, except for those countries, where contact to the previous partners got lost, and where no replacement could be found during the project: Czech Republic, Greece, Iceland, Poland, Spain. Additionally, the information presented in the score cards was cross-checked with the information provided in the national implementation reports (Annex 2) and presentations of national IDB data administrators during IDB-Network meetings.

- Initial status 2015: Inadequacies of national implementations

Score cards have been completed for those 26 countries, which participated in the JAMIE as well as in the BRIDGE-Health project. Table 2 shows average scores for each item, based on these 26 countries in 2015. Perfect implementations in all 26 countries would lead to an average score of 2,0, which was not the case, of course.  For average score below 1,6 short comments inform about the main reasons or challenges.

| Table 2: Average scores (26 countries) by item and main reasons for low scores (2015) |  |  |
| --- | --- | --- |
| Item | Average score | Comments |
| A. Participation in EU-data exchange |  |  |
| 1. Membership as observer or full member NDA-network | 1,8 |  |
| 2. Participation level in past five years | 1,7 |  |
| 3. Government endorsement perspective for NDA-participation | 1,5 | Rather weak governmental support in some countries |
| 4. Responsive to information requests of NDA-coordinator | 1,7 |  |
| A. Subtotal (max. 8) | 6,8 |  |
| B. Data delivery (up to 2014) |  |  |
| 5. Data delivered in past five years (2012-2014) | 1,7 |  |
| 6. MDS data 2014 delivered | 1,3 | Timely delivery is a challenge for some countries. |
| 7. Accuracy of coding (most current delivery) | 1,7 |  |
| 8. Incidence rate | 1,3 | Unbiased and nationally representative samples are a challenge for some countries |
| 9. Consistency of case definition (IDB & HDR or EDR) | 0,9 | In 2015, consistency has not been checked yet for most countries |
| 10. Scope of data collection | 1,5 | Full scope is a challenge for some countries |
| 11. FDS sample 2014 | 0,8 | FDS data collection is a challenge for many countries |
| B. Subtotal (max. 14) | 9,3 |  |
| C. Quality of current system (2015) |  |  |
| 12. Data collection ongoing | 1,6 |  |
| 13. Age groups | 1,5 | Covering all age-groups is a challenge for some countries |
| 14. Injury categories | 1,6 |  |
| 15. Outpatients | 1,5 | Covering out-patients is a challenge for some countries |
| 16. Completeness of coding (mechanism, injury type, body part) | 1,5 | Applying all MDS codes is a challenge of some countries |
| 17. Incidence rates | 1,5 | Unbiased samples are a challenge for some countries |
| 18. Geo-coverage | 1,5 | National coverage is a challenge for some countries |
| 19. Sampling of hospitals | 1,4 | Validated samples are a challenge for some countries |
| 20. Hospital sample size | 1,5 | Sufficient number of reference hospitals is a challenge for some countries |
| 21. FDS data | 1,0 | FDS data collection is a challenge for many countries |
| C. Subtotal (max. 20) | 14,7 |  |
| D. Prospects for 2016+ |  |  |
| 22. Will the MDS data collection continue in 2016? | 1,7 |  |
| 23. Improvement or maintenance plan in place for next years? | 1,3 | Tackling shortcomings of the system is a challenge for many countries |
| 24. Legal basis for MDS data collection? | 1,4 | Many countries collect data only voluntarily |
| 25. Capacities in your organization for injury data collection/ analysis? | 0,9 | Capacity problems due to low priority for injury data and EU health data exchange is a challenge for many countries |
| 26. Interest to participate in future EU injury information projects? | 1,6 |  |
| D. Subtotal (max. 10) | 6,8 |  |
| Total Average (max. 52) | 37,7 |  |

There are considerable variations between countries. Table 3 shows the scores 2015 for the four groups of items. Full implementation of all requirements would lead to a max. score of 52 points. Almost all national implementations show at least a few minor shortcomings.

In 2014, the consistency of inclusion/exclusion criteria for IDB and for the reference statistics was unclear for almost all countries. Additional comments on major shortcomings are given, when the total score falls below 43. For more details see Annex 1, which contains the full table, for all items, all countries and both years 2015 and 2017.

| Table 3: Scores for item-groups by country and main reasons for low scores (2015) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | A. Participation in EU-data exchange | B. Data delivery (up to 2014) | C. Quality of current system (2015) | D. Prospects for 2016+ (2015) | Total score (2015) | Major shortcomings |
| Maximum | 8 | 14 | 20 | 10 | 52 |  |
| AT | 8 | 13 | 19 | 7 | 47 |  |
| CY | 8 | 10 | 16 | 7 | 41 | Biased sample (no private hospitals). No incidence rates. |
| CZ | 3 | 11 | 14 | 6 | 34 | Only data on children 0-18a, only on admissions. No incidence rates. |
| DK | 8 | 13 | 19 | 8 | 48 |  |
| EE | 8 | 10 | 18 | 8 | 44 |  |
| FI | 6 | 8 | 18 | 8 | 40 | Bias toward admissions. Delayed data delivery. |
| GE | 8 | 11 | 16 | 6 | 41 | Small sample. Sampling within hospital. Just one federal state. |
| GR | 1 | 3 | 0 | 0 | 4 | Dropped out during JAMIE-project. |
| HU | 8 | 2 | 0 | 6 | 16 | Dropped out after end of JAMIE-project. |
| IE | 7 | 5 | 13 | 7 | 32 | Just data on persons 15+. Small sample. |
| IS | 4 | 9 | 18 | 6 | 37 | Data collection continued, but data exchange stopped after JAMIE-project. |
| IT | 7 | 9 | 18 | 9 | 43 |  |
| LT | 8 | 10 | 18 | 7 | 43 |  |
| LU | 8 | 13 | 20 | 9 | 50 |  |
| LV | 8 | 14 | 18 | 7 | 47 |  |
| MT | 8 | 9 | 20 | 9 | 46 |  |
| NL | 8 | 13 | 20 | 9 | 50 |  |
| NO | 8 | 11 | 18 | 8 | 45 |  |
| PL | 2 | 3 | 0 | 1 | 6 | Dropped out after end of JAMIE-project. |
| PT | 8 | 10 | 16 | 8 | 42 | Just home & leisure accidents. |
| RO | 6 | 7 | 0 | 3 | 16 | Dropped out after end of JAMIE-project. |
| SE | 8 | 11 | 19 | 8 | 46 |  |
| SI | 8 | 13 | 19 | 9 | 49 |  |
| SP | 6 | 6 | 11 | 6 | 29 | Dropped out after end of JAMIE-project. |
| TR | 8 | 12 | 19 | 9 | 48 |  |
| UK | 7 | 7 | 15 | 7 | 36 | Not all MDS codes implemented. Delayed data delivery. |
| Average (26) | 6,8 | 9,3 | 14,7 | 6,8 | 37,7 | Low score mainly due to six drop-outs. |
| Average without 6 drop-outs (GR, HU, IS, PL, RO, SP) | 7,1 | 10,1 | 16,8 | 7,4 | 41,5 |  |

The average total score for all 26 countries was 37,7. However, six countries discontinued their data collection/submission with the end of the JAMIE-project and EU co-funding: Hungary, Iceland, Poland, Romania, Spain. Greece dropped out already during the JAMIE-project due to the budgetary crisis and austerity measures. The average score for the remaining 20 countries, which managed to continue their data collection system in 2015, without any EU co-funding, was at least 41,5.

- Improvement plans

One objective of the BRIDGE-project was to improve the quality of national IDB systems. The distance of 41,5 points to the possible maximum of 52 points indicates, that many of these sustained implementations suffer from some shortcomings. The score cards indicated inadequacies and recommended improvements. National IDB data administrators promised to strive for these improvements during the BRIDGE-project project, however without binding agreement, as the participation in the IDB-system was and still is voluntary.

Table 4 shows the overall assessment of the 20 national implementations, which exists by the start of the BRIDGE-Health project in 2015 and summarizes briefly, which improvements are necessary for full compliances with the standards.

| Table 4: Total implementation score by country and desired improvements |  |  |  |
| --- | --- | --- | --- |
|  | Total (max. 52) | Major and minor shortcomings | Desired improvements |
| AT | 47 | Weak governmental support. | Seek governmental support and strive for a legal basis. |
| CY | 41 | No valid reference statistic available for establishing valid estimates (no data from private hospitals). No FDS sample. | Control sampling bias (just public hospitals). Seek at least one FDS reference hospital. |
| CZ | 34 | Only data on children 0-18a. No incidence rates. | Seek governmental support and strive for a legal basis for the expansion to all age-groups and all ED treatments (including non-admissions) in order to establish valid national estimates. |
| DK | 48 | Scarce resources threaten data handling. | Seek governmental support in order to increase capacities for data handling. |
| EE | 44 | No FDS sample. | Increase quality of coding. Seek at least one FDS reference hospital. |
| FI | 40 | Bias toward admissions. Delayed data delivery. No FDS sample. | Control admission bias in order to establish valid estimates. Seek at least one FDS reference hospital. Speed up data delivery if possible. |
| GE | 41 | Validated, but small sample (just one hospital) in just one federal state. Bias toward admissions, therefore no automatic calculation of rates possible. | Enlarge hospital sample in state of Brandenburg. Implement MDS data collection for all ED cases (24 hours, 7 days a week). Seek expansion toward other federal states. |
| IE | 32 | Just data on persons 15+. Validated, but small sample (just one hospital). | Enlarge hospital sample. Expand data collection to all age-groups. |
| IT | 43 | Last complete delivery for 2011. Data 2012 and 2013 incomplete; no incidence rates possible. | Work off with data delivery 2012-2014 and secure delivery in time for recent years. |
| LT | 43 | No FDS sample. | Seek at least one FDS reference hospital. |
| LU | 50 |  | No improvement needed. |
| LV | 47 | Bias toward admissions, although corrected incidence rates. | Implement MDS data collection also for ambulatory treatments in sufficiently large sample. |
| MT | 46 | Delay of data delivery 2014. | Speed up data delivery if possible. |
| NL | 50 |  | No improvement needed. |
| NO | 45 | No FDS sample. | Seek at least one FDS reference hospital. |
| PT | 42 | Just home & leisure accidents. Small sample. | Expand data collection to all injuries (including road, work-place and violence). Enlarge hospital sample. |
| SE | 46 | Delay of data delivery 2014. | Speed up data delivery if possible. |
| SI | 49 |  | No improvement needed. |
| TR | 48 | Biased sample toward children. | Seek better balance of the sample. |
| UK | 36 | Not all MDS codes implemented (e.g. falls cannot be identified). Last complete delivery for 2011. | Implement all MDS codes. Work off with data delivery 2012-2014 and secure delivery in time for recent years. |
| Average (20 countries with sustained systems) | 41,5 |  |  |

- Achievements and set-backs: Status of implementations (2017)

Table 5 shows the scores 2015 and 2017 by item-group and total, for 20 countries, which sustained their data collection after the end of the JAMIE-project.

| Table 5: Scores by country 2015 and 2017 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | A. Participation in EU-data exchange |  | B. Data delivery |  | C. Quality of current system in place |  | D. Prospects for the future |  | Total |  | Difference |
|  | 2015 | 2017 | 2015 | 2017 | 2015 | 2017 | 2015 | 2017 | 2015 | 2017 |  |
| Maximum | 8 | 8 | 14 | 14 | 20 | 20 | 10 | 10 | 52 | 52 |  |
| AT | 8 | 8 | 13 | 14 | 19 | 19 | 7 | 8 | 47 | 49 | 2 |
| CY | 8 | 8 | 10 | 11 | 16 | 18 | 8 | 9 | 42 | 46 | 4 |
| CZ | 3 | 2 | 11 | 5 | 14 | 12 | 6 | 7 | 34 | 26 | -8 |
| DK | 8 | 8 | 13 | 12 | 19 | 17 | 8 | 8 | 48 | 45 | -3 |
| EE | 8 | 8 | 10 | 12 | 18 | 18 | 8 | 9 | 44 | 47 | 3 |
| FI | 6 | 6 | 8 | 10 | 18 | 18 | 8 | 8 | 40 | 42 | 2 |
| GE | 8 | 8 | 11 | 11 | 16 | 16 | 6 | 6 | 41 | 41 | 0 |
| IE | 7 | 6 | 5 | 8 | 13 | 11 | 7 | 2 | 32 | 27 | -5 |
| IT | 7 | 8 | 9 | 10 | 18 | 19 | 9 | 9 | 43 | 46 | 3 |
| LT | 8 | 8 | 10 | 10 | 18 | 18 | 7 | 9 | 43 | 45 | 2 |
| LU | 8 | 8 | 13 | 14 | 20 | 20 | 9 | 10 | 50 | 52 | 2 |
| LV | 8 | 8 | 14 | 11 | 18 | 19 | 7 | 9 | 47 | 47 | 0 |
| MT | 8 | 8 | 9 | 10 | 20 | 20 | 9 | 8 | 46 | 46 | 0 |
| NL | 8 | 8 | 13 | 14 | 20 | 20 | 9 | 10 | 50 | 52 | 2 |
| NO | 8 | 8 | 11 | 10 | 18 | 18 | 8 | 9 | 45 | 45 | 0 |
| PT | 8 | 8 | 10 | 12 | 16 | 14 | 8 | 7 | 42 | 41 | -1 |
| SE | 8 | 8 | 11 | 13 | 19 | 17 | 8 | 9 | 46 | 47 | 1 |
| SI | 8 | 8 | 13 | 13 | 19 | 20 | 9 | 9 | 49 | 50 | 1 |
| TR | 8 | 8 | 12 | 12 | 19 | 18 | 9 | 7 | 48 | 45 | -3 |
| UK | 7 | 7 | 7 | 10 | 15 | 15 | 7 | 7 | 36 | 39 | 3 |
| Average (20 countries with sustained systems) | 7,5 | 7,5 | 10,7 | 11,1 | 17,7 | 17,4 | 7,9 | 8,0 | 43,7 | 43,9 | +0,3 |

The results show that generally hardly any progress in terms of quality improvements could be achieved. The average score stayed actually unchanged.

However, some improvements need to be mentioned: The partner in Cyprus (Ministry of Health) found a way to control the sample bias (only public hospitals, and not data from private hospitals) and to provide again national incidence rates. The partner in Finland (national public health institute) detected that erroneously their samples were considered as biased and have corrected all their metadata. The uncertainty about the consistence of case definitions (inclusion/exclusion criteria) in IDB sample and reference statistics (e.g. hospital discharge statistic) could be cleared for almost all countries.

In a few countries the system became under severe pressure due to decreasing resources. The partner in the Czech Republic (a university hospital) maintained its data collection (on childhood injuries), however did not find any resources to continue its collaboration with the EU injury data exchange. The partner in Denmark (the national public health institute) reported increasingly scarce resources, which led to termination of the FDS data collection. The partner in Ireland reported serious capacity problems, which led to substantial delays of data handling and submission. The partner in Turkey had some problems with establishing valid national rates, but seems to solve these very recently.

There are also increasing concerns about delivering individual health records, even when strictly anonymized and without any opportunity to identify individuals. There seems to be quite some uncertainty what the national implementations of new EU General Data Protection Regulation 2016 [13] will imply, which supersedes the old EU Data Protection Directive 1995 [14] and will be enforceable by 2018. Denmark, Sweden and UK have announced that they will put a hold on the further delivery of IDB micro-data, at least as long as there is no clarity on the legitimacy of such delivery. The Netherlands has stopped to deliver narratives, which contain quite valuable information for a better understanding of injury causation. Sweden and Estonia do not allow anymore the disclosure of IDB micro-data for research purposes. Due to national data protection particularities, Italy cannot deliver any IDB micro data to third parties, but only directly to the Commission services (DG Santé).

- Efforts to improve geo-coverage and status (2017)

Increase of the geo-coverage was another objective of the BRIDGE-project. Eligible for participation are 36 European countries, i.e. 28 EU member states, 3 EEA-countries (Iceland, Liechtenstein, Norway) and 5 candidate countries (Albania, Macedonia, Montenegro, Serbia, Turkey). In 2014, a maximum of 25 IDB-countries could be reached, whereof five dropped out after the termination of EU co-funding in 2015. 20 countries remained, which sustained the IDB data collection, entirely with own resources.

There are seven countries, which participated in the data exchange in the past, and should be invited to re-start their collaboration with the IDB-Network (France, Island) or to restart their data collection (Greece, Hungary, Romania, Poland, Spain). Eight other eligible countries should be motivated to implement a national IDB injury surveillance system and to share their data (Albania, Belgium, Bulgaria, Croatia, Serbia, Slovakia, Macedonia, Montenegro), while Liechtenstein with a population of about 37.000 was considered as too small.

Table 6 summarized the status of 2015, acquisition efforts and results in 2017.

| Table 6: Acquisition efforts 2015-2017 and achievements |  |  |  |
| --- | --- | --- | --- |
| Country | Status 2015 | Efforts | Status 2017 |
| Albania | No data, no contact. | Search for competent contact through various channels: WHO focal points for injury prevention; focal points for EU Health programme). Presentations at WHO south-eastern European work-shops on injury surveillance and targeted follow up. | Contact established, but no resources for data collection and active participation in the network. |
| Belgium | No contact. | Search for competent contact through various channels: Focal points for EU Health programme; EU expert group on health information, BRIDGE project leader). | No responsive contact identified. |
| Bulgaria | No contact. | Search for competent contact through various channels: WHO focal points for injury prevention; focal points for EU Health programme). Presentations at WHO south-eastern European work-shops on injury surveillance and targeted follow up. | No responsive contact identified. |
| Croatia | No data, but network member. | Regular information on network-meetings, progress of BRIDGE-project. Presentations at WHO south-eastern European work-shops on injury surveillance and targeted follow up. | Contact sustained, but no resources for data collection and active participation in the network. |
| France | Sustained data collection (home and leisure accidents), but no network member. | Personal contacts to competent authorities and leading persons. | Position remains unchained: No interest to expand system to all injuries and to share data. |
| Greece | Pilot in 2013 stopped due to financial crisis. No new data, but network member. | Regular information on network-meetings, progress of BRIDGE-project. | Contact lost. |
| Hungary | Pilot 2014 stopped after JAMIE-project. No new data, but network member. | Regular information on network-meetings, progress of BRIDGE-project. | Contact sustained. Active participation in the network, but no resources for data collection. |
| Iceland | Sustained data collection. Submission stopped after JAMIE-project, but network member. | Regular information on network-meetings, progress of BRIDGE-project. | No resources for data sharing and active participation in the network. |
| Liechtenstein | No contact. | No action. | No contact. |
| Macedonia | No data, but network member. | Regular information on network-meetings, progress of BRIDGE-project. Presentations at WHO south-eastern European work-shops on injury surveillance and targeted follow up. | Contact sustained, but no resources for data collection and active participation in the network. |
| Montenegro | No data, no contact. | Search for competent contact through various channels: WHO focal points for injury prevention; focal points for EU Health programme). Presentations at WHO south-eastern European work-shops on injury surveillance and targeted follow up. | Contact established, but no resources for data collection and active participation in the network. |
| Poland | Pilot in 2014 stopped after JAMIE-project. No new data, no contact. | Search for competent contact through various channels: WHO focal points for injury prevention; focal points for EU Health programme). Presentations at WHO south-eastern European work-shops on injury surveillance and targeted follow up. | No responsive contact identified. |
| Romania | Pilot in 2014 stopped after JAMIE-project. No new data, but active network member. | Regular information on network-meetings, progress of BRIDGE-project. Presentations at WHO south-eastern European work-shops on injury surveillance and targeted follow up. | Active participation in the network, but no resources for data collection. |
| Serbia | No data, no contact. | Search for competent contact through various channels: WHO focal points for injury prevention; focal points for EU Health programme). Presentations at WHO south-eastern European work-shops on injury surveillance and targeted follow up. | Contact established. Active participation in the network, but no resources for data collection. |
| Slovakia | No data, but active network member. | Regular information on network-meetings, progress of BRIDGE-project. | Contact sustained. Active participation in the network. Implementation of data collection and data sharing planned. |
| Spain | Pilot in 2014 stopped after JAMIE-project. No new data, but network member. | Regular information on network-meetings, progress of BRIDGE-project. | Contact sustained. Active participation in network. Data collection in place, data sharing planned. |

All eligible countries, except Liechtenstein, have been contacted. In countries, where no contact person for the IDB-network was known, a targeted search for competent contacts has been carried out through various channels: WHO focal points for injury prevention [15], focal points for EU Health programme [16], focal points for the implementation of the EU health programme [17] and/or members of the European Expert Group on Health information (EGHI) [18] were contacted and requested to help with identifying competent and interested institutions.

Additionally, for the South-Eastern European region (SEER), the WHO- regional office for Europe organized a series of work-shops on injury surveillance, which attracted governmental representatives from all countries of the region, and which provided an excellent platform for presenting the EU injury surveillance system. The last one of these workshops was held in Chisinau, Moldova on 12-13 November 2015. The meeting explicitly recommended to register all injury related ED cases with a minimum data set like IDB-MDS in order to establish meaningful national injury statistics [19].

By October 2017, for all eligible countries – except Bulgaria, Belgium, Czech Republic, France, Greece, Liechtenstein and Poland – functioning contacts with interested and competent bodies are established. However, despite of all these efforts between 2015-2017, no additional country was able to join the injury data exchange. Main reasons seemed to be austerity budgets as a result of the economic crisis and a general shift of policy priorities, eventually as a result of the refugee crisis. In personal discussions also the Brexit process, defamiliarization between old and new member states and moderation in EU ambitions of some candidate countries were mentioned as reason, why actions on harmonizing European injury information systems did not find more support in recent years.

Considering this general political climate, it seems to be a success, that all 20 European countries of 2015 maintained their IDB injury surveillance system and 19 are still willing and able to continue with data sharing, entirely at own expenses.

- Status of the EU web-gates (2017)

There are three relevant EU web-gates, which shall make IDB data accessible:

- EU IDB public access at https://webgate.ec.europa.eu/idb/public-access/ [6]

- EU IDB restricted access, see https://ec.europa.eu/health/data_collection/databases/idb/restricted_access_en [16]

- ECHI web-site at https://ec.europa.eu/health/indicators/echi/list_en [8]

The web-sites provide different data for different purposes:

- The EU IDB public access allows extremely variable analyses of IDB-MDS data [20]. The user can select subgroups by using all IDB-MDS data elements as selection criteria, not just country, year and age-group, but also type of injury, activity and location.

- The EU IDB restricted access allows analyses of IDB-FDS data [21]. However, eligible are only the data providers themselves, and – under certain circumstances – researchers. Main focus of IDB-FDS data is information on involved products, e.g. vehicles, toys, electrical appliances, building components.

- The ECHI web-site provides aggregated data, i.e. national incidence rates of European Core Health Indicators (ECHIs). Main purpose is the comparison of national rates, for the evaluation of EU-level actions. One IDB based indicator is e.g. ECHI-29b “Home, leisure and school accidents” (ECHI-29b), which should be available by country, year, gender and age-group [9].

All these web-gates suffer from serious delays in uploading available data, due to various reasons. At present, the two IDB web-gates contain data just up to 2014, although data of 2015 and 2016 have already been delivered.

The ECHI web-gate does not contain any data yet, although e.g. ECHI-29b is available already since 2009 for certain countries. For the quality of this data, see the metadata for ECHI-29b [22]. It is clear, that the lack of up-to-date information hampers the data use, but also the motivation of data suppliers.

Moreover, the user-friendliness of the EU IDB web-gates is limited. The IDB public access and the ECHI-web-gate support the comparison of country-rates for pre-selected groups of injuries. Other analyses as presented in the report “Injuries in the European Union” [5] or at the EuroSafe web-gate [23] need e.g. cross-tabulations of types of injury, injury mechanisms, places of occurrence, or activities by gender and age-group. Such analyses are cumbersome with the given tools, require many queries and rather complicated additional calculations. Currently also EU- averages are not available. The time-gap in updating and severe shortcomings in user-friendliness required main users to maintain a separate database.

Even more complicated is the access to IDB-FDS data, which is mainly necessary for deeper analyses of the circumstances of injuries, and the role that products eventually play in the causation of incidences and/or injuries. Disclosure of micro-data need to be agreed by every single data supplier, which implies a rather bureaucratic procedure for researcher, network-coordinator, data supplier and databank-operator. Additionally, the web-gate tools for retrieving IDB-FDS data are not facilitating data-analyses as frequently desired by researchers. These circumstances prevent national or EU consumer safety administrators [24] from making use of IDB-FDS data.

A list of desired corrections and amendments of the public access (IDB-MDS web-gate) has been compiled and notified to DG Santé by May 2017, but have not been implemented yet. This list is annexed to this report as Annex 3.

- Perspectives for the future

For assessing the sustainability of the IDB data exchange, a SWOT-analysis has been carried out. These are the main conclusions:

Strengths:

- Relevance: Injury is a major health problem; any public health action in this respect need a meaningful surveillance system. Almost all national governments showed interest in the EU IDB methodology.

- Comparability: IDB based indicators are comparable between countries, years but also between all major domains of prevention: Road safety, work-place safety, consumer safety, child safety, prevention of violence, suicide prevention. The quality of IDB data is good enough for being accepted to provide ECHI-29b for the ECHI web-gate.

- Methodology: The IDB methodology is well elaborated, standardized and comprehensively laid down in the “IDB Operating Manual”. Training materials and tools facilitate implementation and operation at national and EU level.

- Number of participating countries:  Currently (in 2017), 19 European countries (17 EU member states) operate stable IDB systems and are willing to share their data, even without any EU co-funding.

- Dedicated network members: The network consists of very dedicated and extremely experienced and collaborative partners, including the members of the IDB Advisory Board. These partners contributed much to develop the current standards and are willing to continue in the future.

- Costs: The costs per case are rather low, the burden to patient and hospital staff minimal, as IDB-MDS data elements get recorded in usual patient’s history anyway. In many countries, IDB data can be extracted from already existing registries, which have been implemented for other indispensable purposes, e.g. compensation of medical services.

Weaknesses:

- Relevance: There are other groups of diseases, which are perceived as being of greater impact on health and which get more political attention, also due to the fact that the medical profession and the health industry, including pharmaceutical branch, tend to invest in the ‘big five’ (cancer, heart diseases, respiratory diseases, NCD’s).

- Comparability: For certain domains of injury-prevention, there are traditional monitoring systems in place, e.g. based on police-data. These policy sectors prefer having their own, specialized monitoring system instead of a universal health-information based data system. Comparing national rates is not always of national political interest.

- Methodology: Some of the national IDB-implementations have their shortcomings, e.g. small or biased samples, limited scope of data collection (e.g. just home & leisure accidents), or limited geo-validity (e.g. just based on one federal province).

- Number of participating countries: 17 EU member with an IDB system mean that there are 9 more without. Among the countries without system are the larger EU countries like France, Poland, Spain.

- Costs: Although the costs per case are low, operating an IDB system still requires some capacities within hospitals, data administrating national agencies, national governments (ministries of health) and legislative bodies, and EC administration (qualified staff, financing, IT, administrators). These costs are the main obstacle for potential new-comers, in particular for less well-resourced countries in the South-Eastern European region.

Threats:

- Administrative burden: The burden for national data suppliers and central services has increased over past years. While originally just IDB-FDS data were collected, data suppliers are now requested to deliver IDB-FDS data files (from at least one IDB-FDS reference hospital), a list of IDB-FDS reference hospitals, IDB-MDS data files (from a sample of hospitals as large as possible), completed metadata forms, and reference population data files, which define the national incidence rates for both sexes and each year of age. Some countries deliver data only directly to DG Santé. In the future, when also ECHI-indicators will have to be delivered to the ECHI-database, additional templates have to be completed by these countries.

- Data protection: There are increasing concerns about handling individual health data, even when anonymized and not identifiable. There seems to be quite some uncertainty regarding the national implementations of new EU General Data Protection Regulation 2016 [13] which supersedes the old EU Data Protection Directive 1995 and will be enforceable by 2018. At least at present, the number of national particularities increases. Without legal obligation, some countries will not deliver health related micro-data anymore.

- Changing and contradictory EU ambitions: The EU’s vision regarding the need for and the most appropriate strategy for a joint injury surveillance system is constantly changing. Since its beginning in the eighties, EU-funding of the injury data exchange was only through temporary projects. While the system was originally designed to deliver details on consumer products, it is now to produce comparable national health indicators, and obviously shall in the future support medical research. The recent call for a joint action on health information, action no. 2.2.3.2 [25] explicitly requested to secure the operation of existing EU level data exchange, but the actually commissioned project does not provide any co-funding for particular health information exchange networks such as the IDB, which jeopardizes the investments of many years made by EC and member states.

- General policy priorities: E.g. the economic crisis, the refugee crisis, insufficient economic convergence and geo-political competition change the political priorities for the EU and may contribute to a decreasing ambition of member states to invest into health data exchange systems. Without any new initiatives and appealing selling propositions, the number of countries participating in IDB can further shrink in coming years.

- Funding for EU level support: Operating an EU data exchange need some central services, not just an IT-infrastructure, but also central validation of data, and an help-desk for answering technical questions of data suppliers, and maintaining standards and tools etc.

Opportunities:

- Administrative burden: New technologies promise a significant reduction of the burden of collecting health data in hospitals, e.g. voice recording, automatic coding, extracting (trans-coding) of data from other registries. The burden for national data administrators and EC services can be also reduced by focussing on the future main purposes of the EU injury surveillance system. If there is no further interest in product related injury data, eventually IDB-FDS can be dropped, and focus can be set on IDB-MDS data.

- Data protection: The availability of micro-data allows most flexible selections of sub-groups and most complex analyses, as e.g. desired by researchers. However, aggregated data, e.g. pre-set templates as needed for the ECHI data-bank (ECHI-29b, ECHI-30b, ECHI-31 etc.) would probably solve the data protection problem, at least for macro-data analysis purposes.

- Changing EU ambitions: The intended creation of a European Research Infrastructure Consortium for Health Information, co-funded by Member States and EU research funds provides new funding opportunities. A new health information framework under the auspices of DG Research may attract new countries and new policy sectors, which are better resourced than public health.

- Funding for EU level support: For the next couple of years, the EC intends to continue to outsource the maintenance of its central health information portals which provides also support for the maintenance of the IDB-web gate and -helpdesk. It is important that the IDB-part of the EC-health database is receiving sufficient attention and updates are uploaded faster than what we have seen over the past few years.

With the end of the previous EU-project JAMIE in 2014, any co-funding of national IDB data collection, handling and submission was terminated. Subsequently, four out of 25 countries did not continue to collect IDB data. These four countries have carried out pilot implementations, but were not able to lead over to permanent implementations without further EU subsidies. A fifth country maintained the national data collection but decided to refrain from further data sharing, so that in 2015, when the BRIDGE-Health project started, 20 countries operated IDB injury surveillance system and shared their data. During 2016-2017 another country stopped the delivery of still collected data.

Currently (in 2017), 19 countries operate an IDB data collection and are able and willing to provide their data for being uploaded to the respective EU databases. These countries, whereof 17 are EU member states, seem to have rather stable systems, which probably will be sustained also in the future (2018+). All these countries have expressed their interest to continue, rather independent from the question, how the organizational framework of a future EU health information system will look like.

In conclusion:

Although much needed EC-funding for the operation of the EU injury data exchange is discontinued from 30 November 2017 due to the end of the BRIDGE-project, the IDB-Network members are looking forward to continuing their exchange and collaboration in the coming three years, at least as long as the EC hosts the data. The vision of the IDB-network, currently coordinated by EuroSafe, as to the immediate future is:

- Continuation of MDS-level data collection in countries is a priority and to ensure continuous quality improvement. Therefor EuroSafe will continue to support competency development, quality assurance, and data pooling and summary reporting at EU-level.

- As to the data pooling of MDS-level data, the IDB-members have to look for simpler procedures than the time-consuming handling of micro-data at EU-level. As there are also growing concerns about data confidentiality and reluctance among the IDB-partners to send micro-level data to an open database, Eurosafe will explore opportunities to exchange national data at an aggregated level. The use of pre-set tables as template for national data presentation allowing these to be collated into a pre-defined set of EU-level data presentations would circumvent current data protection concerns and simplify the production of EU-level summary reports on IDB.

- As to FDS-data, for many countries these data can be provided in the slipstream of the production of MDS-level data presentation. It is however up to the EC to decide how to handle the exchange of such micro-level data, given the rising concerns about data protection.

For the time being, the Network coordinator is of the opinion that FDS-level data should be primarily used and analysed at country level and will encourage IDB-members to seek collaboration with other members to broaden their analyses under supervision and authority of the involved countries.

- As JRC is looking into the relevance of FDS-level IDB for consumer protection policies [26], the Network has to wait for the JRC-report and following decisions by the EU-Member States as to the need for enhancing product-related injury surveillance and the role IDB and its network of partners could serve in this respect.

In summary this means that:

- For the sake of simplicity and data confidentiality, it is recommended to seek opportunities for having MDS-data exchange among the IDB-members limited to aggregated level data only. A set of tables shall be developed and the feasibility of such an exchange tested.

- EuroSafe will encourage continued annual data uploads of IDB-data into the EU-web gate, for FDS-level data [6]. However, this exchange should take place under the responsibility of the respective national and EU-authorities. For that reason, the IDB data validation and upload tool [27] should be in due course transferred to the EC-web gate.

- EuroSafe will encourage the IDB-partners to engage in collaborating studies and analysis of data in order to produce robust multi-country presentations of injury data. The IDB-Advisory Board members are best placed to take a lead in such initiatives, as they did in the past few years.

- The network partners will need to continue to invest in keeping competencies of staff in countries up to date (maintenance of the Operating Manual, regular training events and webinars, E-updates) and in liaising with stakeholders in countries and at EU-level in order to secure a sustainable role of IDB in future health- and consumer policy-information systems.

- References

[1] EuroSafe (2016): EU-IDB Operating Manual. http://www.eurosafe.eu.com/uploads/inline-files/IDB_operating_manual_Jan%202017_0.pdf

[2] Eurostat (2017): Euro-SDMX Metadata structure. http://ec.europa.eu/eurostat/data/metadata/metadata-structure

[3] ECHIM – European Community Health Indicators Monitoring (2011): ECHI shortlist and documentation sheets for injury indicators 29–32.   http://www.healthindicators.eu/object_document/o5956n29063.html

[4] Rogmans W (2012): Joint action on monitoring injuries in Europe (JAMIE). Arch Public Health, 2012, 70(1). https://www.ncbi.nlm.nih.gov/pubmed/22958448

[5] EuroSafe (2016): Injuries in the European Union, issue 6 – Summary of injury statistics for the years 2012-2014. http://www.eurosafe.eu.com/uploads/inline-files/EuropeSafe_Master_Web_02112016%20%282%29.pdf

[6] The BRIDGE-Health project (2016). http://www.bridge-health.eu/ and  http://www.bridge-health.eu/sites/default/files/Booklet_HealthBridge_final.pdf

[7] Eurosafe (2017): Injury in the European Union 2013-2015/ Supplementary report to the 6th edition of “injuries in the EU”. http://www.eurosafe.eu.com/uploads/inline-files/IDB%202013-2015_suppl%20to%206th%20edition%20Injuries%20in%20the%20EU.pdf

[8] EU IDB – European Injury Data Base (2016). At: https://webgate.ec.europa.eu/idb/

[9] ECHI – European Core Health Indicators (2016). At: http://ec.europa.eu/health/indicators/echi/list/index_en.htm

[10] BRIDGE-Health project (2017): Policy paper on an European Research Infrastructure on Health Information. http://www.bridge-health.eu/sites/default/files/Policy%20paper_ERIC_HealthInformation_FINAL.pdf

[11] Rogmans W (2012): Joint action on the monitoring injuries in Europe (JAMIE). Arch Public Health 2012, 70(1), p19. http://www.ncbi.nlm.nih.gov/pubmed/22958448

[12] Eurosafe (2017): Documents of the network of IDB data suppliers. http://www.eurosafe.eu.com/key-actions/injury-data/toolbox

[13] Regulation 2016/679 of the European Parliament and of the Council of 27 April 2016 on the protection of natural persons with regards to the processing of personal data.  http://ec.europa.eu/justice/data-protection/reform/files/regulation_oj_en.pdf

[14] EU Data Protection Directive 1995 Directive 95/46/EC of the European Parliament and of the Council of 24 October 1995 on the protection of individuals with regard to the procession of personal data. http://eur-lex.europa.eu/LexUriServ/LexUriServ.do?uri=CELEX:31995L0046:EN:HTML

[15] WHO (2017): European network of national WHO focal persons for injury prevention http://www.euro.who.int/en/health-topics/disease-prevention/violence-and-injuries/country-work/european-network-of-national-focal-persons

[16] Directorate-General for Health and Food Safety (DG SANTE): National focal points for the third programme of the Union’s action in the field of health (2014-2010). https://ec.europa.eu/health/sites/health/files/programme/docs/nfp_en.pdf

[17] Consumers, Health, Agriculture, Food Executive Agency (CHAFEA): National focal points for EU Health programme. http://ec.europa.eu/chafea/health/national_focal_points.html

[18] Directorate-General Health and Food Safety (DG SANTE): The Expert Group on Health information (EGHI). https://ec.europa.eu/health/indicators/expert_group_on_health_information_en

[19] WHO Regional office for Europe: Meeting report on the South-eastern Europe sub-regional workshop “Improving capacity through improved injury surveillance” in Chisinau, Moldova, 12-13 November 2015. http://www.euro.who.int/__data/assets/pdf_file/0006/298662/SE-Europe-HN-workshop-12-13Nov-15-meeting-report.pdf

[20] EuroSafe (2013): The IDB Minimum Data Set (IDB-MDS) Data Dictionary.   http://www.eurosafe.eu.com/uploads/inline-files/IDB_MDS_Data_Dictionary_JAN%202017.pdf

[21] Eurosafe (2017): The IDB Full Data Set (IDB-FDS) Data Dictionary. Version 1.4.  http://www.eurosafe.eu.com/uploads/inline-files/IDB%20FDS%20Data%20Dictionary%20May%202017_0.pdf

[22] EuroSafe (2016): Injury Database – Minimum Data Set (IDB-MDS) Reference Metadata in ESMS. At: http://www.eurosafe.eu.com/key-actions/injury-data/toolbox

[23] EuroSafe (2016): Look at the figures. At: http://www.eurosafe.eu.com/look-at-the-figures

[24] Directorate-General Justice and Consumer (DG JUST): Consumer Safety Network. http://ec.europa.eu/consumers/consumers_safety/cooperation_with_stakeholders/index_en.htm

[25] Directorate-General for Health and Food Safety (DG SANTE): Third EU health programme 2014-2020, annual work plan for 2017, call for proposals. 2.2.3.2 Joint Action on Health Information towards a sustainable EU health information system that supports country knowledge, health research and policy-making. https://ec.europa.eu/health/programme/events/adoption_workplan_2017_en

[26] Joint Research Centre (JRC): Injury and accident data collection efforts in Europe in support of consumer product safety. http://publications.jrc.ec.europa.eu/repository/handle/JRC102781

[27] Swansea University Medical School (2013): IDB data validation and upload tool: At: https://www.injuryobservatory.net/jamiedatavalidator/login

Annex 1: Table “IDB Implementation scores by country and year” 2015 and 2017

Annex 2: IDB implementation score card reports 2015 and 2017, for 26 countries:

Austria, Cyprus, Czech Republic, Denmark, Estonia, Finland, Germany, Greece, Hungary, Ireland, Iceland, Italy, Lithuania, Luxembourg, Latvia, Malta, Netherlands, Norway, Poland, Portugal, Romania, Sweden, Slovenia, Spain, Turkey, United Kingdom.

National IDB Implementation Score Card Report

Country: AUSTRIA

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 2 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 1 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 2 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 13 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 1 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  | FDS=MDS. About 10000 cases from 5 hospitals in 2014 |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 19 |  |  |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 2 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 0 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 7 |  |  |
| Summary Implementation Assessment |  |  | Excellent and sustainable system. Main shortcoming is the lack of a legal basis. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Vienna |  |  | Robert Bauer |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 11 September 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: CYPRUS

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 1 |  | For 2013 & 2014 no IR provided. |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 1 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 10 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 1 |  | Bias due to lack of statistics from private hospitals |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 1 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 16 |  |  |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 2 |  | Sample bias shall be controlled in order to provide national IR |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 1 |  | unclear |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  | Less capacities for FDS, but more for MDS |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 8 |  |  |
| Summary Implementation Assessment |  |  | Very good system due to the opportunity to extract MDS from public hospital statistics. Main shortcomings are the lack of national estimates (IRs) and FDS data. However, it is planned to control the bias of public hospitals and to provide IRs also retrospectively. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Nicosia |  |  | Pavlos Pavlou |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: CZECH REPUBLIC

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 0 |  | Only first NDA meeting. |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 0 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 1 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 3 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  | 2011+2012 delivered as Excel |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 1 |  | Not yet |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  | To be checked |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 0 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 1 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 0 |  | Only 0-18, only admissions |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 1 |  | Not yet |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 7 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 0 |  | Only children (0-18a) |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 0 |  | Only admissions |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 0 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  | Not necessary due to large sample of hospitals |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  | FDS=MDS |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 14 |  |  |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  | MDS for all admissions, all age groups starts in 2015, IDB-FDS data only for children |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 1 |  | Need second data supplier for MDS for all admissions |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  | Legislation shall introduce MDS for all admissions, all age groups |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 0 |  | Unknown who will handle MDS for all age groups and will be in the position to deliver data to the IDB database |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 6 |  |  |
| Summary Implementation Assessment |  |  | Sustainable implementation on child injuries. Major shortcoming is the lack of governmental support to expand this system to other age-groups and ambulatory treatments. However, due to new legislation MDS data will become available in forthcoming years. Currently it is unknown, how will handle this data. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Brno |  |  | Ladislav Planka |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: DENMARK

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 2 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 1 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 2 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 13 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 1 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 19 |  |  |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  | FDS not secured |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 2 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  | stable |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 1 |  | There are virtually no internal resources |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 8 |  |  |
| Summary Implementation Assessment |  |  | Excellent and sustainable implementation. Improvement recommended regarding capacities. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Copenhagen |  |  | Bjarne Laursen |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: ESTONIA

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  | We have been participating in the network , different projects and events since IDB1 project |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  | Start 2012 |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 1 |  | Average about 17% in 2012 |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 2 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 1 |  | Tb checked |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 10 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  | Validation not necessary due to large sample |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 18 |  |  |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  | ICD10>MDS |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 1 |  | Seek for FDS reference hospital |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 8 |  |  |
| Summary Implementation Assessment |  |  | Excellent system regarding MDS. Main shortcoming is the lack of FDS data. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Tallinn |  |  | Liis Roovali |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: FINLAND

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 1 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 1 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 6 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  | Start 2010 |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 1 |  | Tb checked (bias toward admissions?) |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 1 |  | 2014 not available yet |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 1 |  | Tb checked |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 1 |  | Admission bias |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 8 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  | Bias toward admissions (75% in 2012) or confusion of coding? |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  | Not necessary due to full coverage |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  | Not necessary due to full coverage |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 18 |  |  |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 1 |  | Seek FDS reference hospital |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  | Implemented by administrative act. Based on hospital register |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 8 |  |  |
| Summary Implementation Assessment |  |  | Sustainable implementation. Shortcomings are the lack of FDS data and underreporting of ambulatory treatments, which leads to an underestimated rate. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Helsinki |  |  | Markus Grönfors |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: GERMANY

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 1 |  | Automatic calculation of IR not possible at the IDB web-gate. IR provided in metadata. |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 2 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 0 |  | Rate valid only for Brandenburg, small sample, bias toward admissions |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 2 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 11 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  | FDS>MDS |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 1 |  | Biased toward admissions |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 1 |  | Valid only for Brandenburg |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 1 |  | Just 1 hospital: Cottbus general hospital |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 1 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 16 |  |  |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  | FDS>MDS |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 1 |  | Inclusion of other hospitals in Brandenburg for FDS? Expansion to other federal States? |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 0 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 6 |  |  |
| Summary Implementation Assessment |  |  | Stable system, sufficient for providing IRs for state of Brandenburg, but not for entire Germany. Major shortcomings are the restriction to just one federal state and the small sample. There is no constitutional responsibility at federal level, which hampers national implementation. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Potsdam |  |  | Gabriele Elsässer |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: GREECE

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 1 |  |  |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 0 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 0 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 0 |  | No response on invitation to join BRIDGE project |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 1 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 1 |  | Just 2012 |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 0 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  | 2012 |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 0 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 0 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 0 |  | Sample small, no IR |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 4 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 0 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 0 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 0 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 0 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 0 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 0 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 0 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 0 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 0 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 0 |  | No system in place |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 0 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 0 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 0 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 0 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 0 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 0 |  | No competent partner available |
| Summary Implementation Assessment |  |  | A promising start-up implementation had to be discontinued due to governmental austerity measures. Data of the temporary implementation 2012 were delivered. Since 2014 no responses of previous JAMIE partner. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Athens |  |  | Vasillios Makropulos |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: HUNGARY

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 0 |  | Just 2013 FDS>MDS |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 0 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  | 2013 |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 0 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 0 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 0 |  | No IR, no children, no burns, just one hospital |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 2 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 0 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 0 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 0 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 0 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 0 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 0 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 0 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 0 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 0 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 0 |  | No system in place |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 1 |  | It is likely, that legislation will provide the basis |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 1 |  | Legislation shall introduce MDS data collection as a matter of routine |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 1 |  | Legislation shall introduce MDS data collection as a matter of routine |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 6 |  |  |
| Summary Implementation Assessment |  |  | Successful pilot FDS implementation in one hospital, which discontinued with the end of the JAMIE project. Ongoing substantial discussion about legislation, which shall make the MDS data collection compulsory for all hospitals, has been initiated. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Budapest |  |  | Péter Varsány |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: IRELAND

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 1 |  | MoH support unclear for BRIDGE project |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 7 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 0 |  | Just 2013 |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 1 |  | Not yet |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  | 2.3% in 2013 |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 1 |  | 2013 |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 1 |  | unclear |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 0 |  | No children, small sample |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 5 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 0 |  | Children 0-15y not covered. |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 1 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 1 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 1 |  | Just 1 hospital |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  | Just MDS |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 13 |  |  |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 1 |  | Efforts ongoing to expand current dataset |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 1 |  | There are efforts being made to promote the JAMIE model as a template for data collection in Irish EDs. |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 7 |  |  |
| Summary Implementation Assessment |  |  | Promising start-up implementation. However, just one hospital, just MDS, just age 16+. Sustainability unclear, data delivery for 2014 not (yet) achieved |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Cork |  |  | Eve Griffin |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: ICELAND

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 1 |  | Active during JAMIE |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 1 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 1 |  | Unclear for BRIDGE |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 1 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 4 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  | 2010-2013 |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 1 |  | Not yet delivered |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  | 2010-2013 |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 1 |  | 2010-2013 |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 1 |  | unclear |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 9 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  | Hospital located in capital; however, the catchment area is the whole country. |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  | Just one hospital, however, it covers approximately 70% of all inpatient discharges in the country. |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 18 |  |  |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 1 |  | Data collection will continue but exchange uncertain |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 1 |  | Not decided |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  | For data collection yes, but not for exchange |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 1 |  | Uncertainty as regards staffing for centralized collection and processing of MDS data. |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 6 |  |  |
| Summary Implementation Assessment |  |  | Sustainable system, but no decision if data will be shared at EU level. Main shortcoming is the lack of FDS data collection. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Reykjavik |  |  | Gudrun Gudfinnsdottir |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: ITALY

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 1 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 7 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 1 |  | Not yet |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 1 |  | 2012 last delivery |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 1 |  | Tb checked |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 1 |  | Only HLA (FDS 2013) |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 1 |  | Not yet |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 9 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 1 |  | FDS and MDS collected, but delivery delayed |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 1 |  | Current FDS only HLA, future MDS without restrictions |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 1 |  | Tb checked |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  | Not necessary due to large MDS sample |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 18 |  |  |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 2 |  | Additional MDS without restriction of scope from 2014 onward |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  | In place for FDS |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 9 |  |  |
| Summary Implementation Assessment |  |  | Excellent and sustainable system. Major shortcomings are that incidence rates are available only for 2011 and 2012, and delays in data delivery. Minor shortcoming is the restricted scope of FDS data collection (only home accidents, road traffic accidents, violence). |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Rome |  |  | Alessio Pitidis |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: LITHUANIA

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 1 |  | About 16% in 2013 |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 2 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 1 |  | Tb checked |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 10 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  | Since 2013 also outpatients |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  | Not necessary due to large sample size |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  | Not necessary due to large sample size |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 18 |  |  |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 1 |  | Search for FDS reference hospital |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 7 |  |  |
| Summary Implementation Assessment |  |  | Excellent and sustainable system. Main shortcoming is the lack of a FDS data. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Vilnius |  |  | Rita Gaidelyte |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: LUXEMBOURG

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  | 2012-2014 |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 2 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 1 |  | Tb checked |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 2 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 13 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 20 |  |  |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 2 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 9 |  |  |
| Summary Implementation Assessment |  |  | Excellent and sustainable system. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Luxembourg |  |  | Dritan Bejko |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: LATVIA

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 2 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 1 |  | Tb checked |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 2 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 13 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 0 |  | Almost complete for admissions; outpatients underrepresented. |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  | Some problems with one statistical region. No problem with representation urban/rural. |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  | Not necessary due to large sample size |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  | FDS>MDS |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 18 |  |  |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 1 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 1 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 7 |  |  |
| Summary Implementation Assessment |  |  | Excellent system due to a solid legal basis. Main shortcoming is the bias towards admissions. However, the IRs generated automatically at the EU IDB web-gate are corrected for this bias, valid estimates for all ED cases available. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Riga |  |  | Jana Lepiksone |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: MALTA

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 1 |  | Not yet due to IT problem |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 1 |  | About 11% in 2011. Not reported for 2013 |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 1 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 1 |  | unclear |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 1 |  | Not yet |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 9 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  | Two of two hospitals |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  | FDS>MDS |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 20 |  |  |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 2 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  | Implemented by administrative act |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 9 |  |  |
| Summary Implementation Assessment |  |  | Excellent and sustainable system. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | La Valetta |  |  | Audrey Galea |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: NETHERLANDS

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 2 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 1 |  | Tb checked |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 2 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 13 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 20 |  |  |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 2 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  | Implemented by administrative act |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 9 |  |  |
| Summary Implementation Assessment |  |  | Excellent and sustainable system. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Amsterdam |  |  | Huib Valkenberg |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: NORWAY

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  | 2012-2014 |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 2 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 1 |  | Tb checked |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 11 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  | Validation not necessary due to large sample |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 18 |  |  |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  | Extracted from central health register |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 1 |  | Search for FDS reference hospital |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 8 |  |  |
| Summary Implementation Assessment |  |  | Sustainable system. Main shortcomings are the lack of FDS data. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Oslo |  |  | Johan Lund |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: POLAND

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 0 |  | Only during JAMIE |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 0 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 0 |  | Only for JAMIE |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 0 |  | Dropped out after JAMIE |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 2 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 1 |  | Only 2013 |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 0 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  | 2013 |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 0 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 0 |  | No IR |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 0 |  | Only children, small sample |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 3 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 0 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 0 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 0 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 0 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 0 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 0 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 0 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 0 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 0 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 0 |  | There is no system in place |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 0 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 1 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 0 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 0 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 0 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 1 |  | Competent partner need to be found |
| Summary Implementation Assessment |  |  | Successful JAMIE pilot in the Wielkopolska region could not be continued; expansion to other hospitals (other age-groups) failed. Other competent and interested authority need to be found for the BRIDGE project. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Poznan |  |  | Mariusz Sykala |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: PORTUGAL

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  | FDS>MDS |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 1 |  | 37% unknown in 2014 |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 2 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 1 |  | Tb checked |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 0 |  | Only home and leisure accidents. Small sample |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 2 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 10 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  | FDS>MDS |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 1 |  | Only home and leisure accidents |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 1 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 0 |  | About 4000 cases from 4 hospitals. |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 16 |  |  |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 1 |  | Larger sample? Extension to all injuries? |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 8 |  |  |
| Summary Implementation Assessment |  |  | Sustainable system. Main shortcoming is the restriction to home and leisure accidents. Minor shortcoming is the relatively small samples of MDS hospitals and cases. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Lisbon |  |  | Teresa Contreiras |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: ROMANIA

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 0 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 6 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 1 |  | Only 2013 |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 0 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  | 5.4% in 2013 |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 1 |  | 2013 |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 1 |  | unclear |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 7 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 0 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 0 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 0 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 0 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 0 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 0 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 0 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 0 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 0 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 0 |  | There is no system in place |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 0 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 1 |  | Search for competent & interested competent authority |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 0 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 1 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 3 |  |  |
| Summary Implementation Assessment |  |  | Successful pilot implementation in 2012/2013 could not be sustained. Main shortcoming is the lack of governmental support. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Cluj-Napoca |  |  | Diana Rus |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: SWEDEN

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 1 |  | Not yet |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  | 3.4% in 2013 |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 1 |  | Not yet |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 1 |  | Tb checked |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 2 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 11 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  | NOMESCO>FDS>MDS |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 1 |  | Comparing data, but no deeper analysis |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  | 7 hospitals |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 19 |  |  |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 2 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 1 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 8 |  |  |
| Summary Implementation Assessment |  |  | Excellent and sustainable system. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Stockholm |  |  | Pernilla Fagerström |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: SLOVENIA

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  | FDS+MDS ICD10>MDS |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  | 6.7% in 2014 |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 2 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 1 |  | tb checked |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 2 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 13 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 1 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 19 |  |  |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  | Not likely, but eventual some problems due to funding reasons |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 2 |  | Not necessary – there should be a major renovation of Out-patient information system in 2015 |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  | Health care databases act |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 9 |  |  |
| Summary Implementation Assessment |  |  | Excellent and sustainable system. Minor shortcoming is that not all FDS variables are covered. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Ljubljana |  |  | Tina Zupanič |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: SPAIN

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 1 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 1 |  | Yes for JAMIE, for BRIDGE unclear |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 6 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 1 |  | FDS>MDS Only 2013 |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 0 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 1 |  | About 20% in 2013 |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 1 |  | For 2013 |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 1 |  | Tb checked |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  | 2013 |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 6 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 1 |  | Restart planned in Catalunya |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 0 |  | Unclear, no data yet available |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 1 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 1 |  | Valid for Catalunya |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 1 |  | unclear |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 1 |  | unclear |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  | Not available for Catalunya |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 11 |  |  |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 1 |  | Foreseen from Catalonia from 2014 onward. Shall be available by the end of 2015 |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 1 |  | Switch from Navarra to Catalunya |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 1 |  | unclear |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 6 |  |  |
| Summary Implementation Assessment |  |  | Successful pilot implementation in one hospital in the region of Navarra. Data collection in Navarra discontinued after JAMIE. MDS data shall become available from Catalunya, from 2014 onward. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Barcelona |  |  | Catherina Perez |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: TURKEY

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 1 |  | Not reported yet |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 2 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 1 |  | Tb checked |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 2 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 12 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  | FDS>MDS |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 1 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  | 15 hospitals but just about 22000 cases |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 19 |  |  |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 2 |  | It is planned to collect MDS from all EDs and continue to collect FDS from 15 hospitals |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 9 |  |  |
| Summary Implementation Assessment |  |  | Excellent and sustainable implementation. Minor shortcomings are the sampling within hospitals, which is not controlled yet. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Ankara |  |  | Cecil Sis |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: UNITED KINGDOM

August 2015

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the seven meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 1 |  | Endorsement for a harmonized system needed from England, Wales, Scotland and Northern Ireland. |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 7 |  |  |
| B. Data delivery (up to 2014) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2009-2014) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  | Currently just 2010 + 2011 available |
| - MDS data 2014 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 0 |  | Not yet |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 1 |  | 14.1% in 2011 |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 1 |  | 2011 |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 1 |  | Tb checked |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2014 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 7 |  |  |
| C. Current system in place (2015) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 0 |  | Currently not possible to identify fall and road location injuries due to limitations of English injury surveillance dataset being used at present |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 1 |  | Only England at present is represented. |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  | Not needed due to large sample |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  | No FDS reference hospital yet |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 15 |  |  |
| D. Prospects for 2016-2017 |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2016? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | No substantial improvements necessary | 2 | 1 |  | Inclusion of Wales & Scotland. Full implementation of MDS. Search for FDS hospital. |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 1 |  | Extraction from existing registers |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 7 |  |  |
| Summary Implementation Assessment |  |  | Sustainable system. Main shortcoming is the lack of FDS data and that falls & road injuries cannot be identified. Minor shortcoming is the lack of timeliness of delivery due to high coordination efforts. |  |  |  |  |  |  |  |  |
| Signatures |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | Signature |  |
| National IDB data administrator |  | Swansea |  |  | Samantha Turner |  |  |  |  | OK for JAMIE final score card June 2014 |  |
| BRIDGE-Health IDB |  | Vienna, 16 October 2015 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: Austria

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2014 | 2 | 2 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Fully consistent | 2 | 2 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 2 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 14 |  |  |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 1 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 19 |  |  |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 2 |  | Extension of sample planned |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 0 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 2 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 8 |  |  |
| Summary Implementation Assessment |  |  | Excellent and sustainable system. Major shortcoming is the lack of a legal basis. During 2015-2017, no substantial changes have taken place. Future participation in the EU IDB data exchange is very likely. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  | Vienna, October 2017 |  |  | Robert Bauer |  |  |  |  | yes |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | yes |  |

National IDB Implementation Score Card Report

Country: CYPRUS

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 2 |  | Reference population file for 2016 has been sent but unfortunately data are inconsistent due to the fact that IDB admissions are under recording. |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 1 |  | Complications and sequels of medical interventions not excluded |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 11 |  |  |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  | Data are available for five public hospitals (MDS) |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 18 |  |  |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 2 |  | Change the procedure of data collection. Medical doctors must fill all of the required fields regarding type of injury, nature of injury, admission in the hospital etc. |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  | We are in the process for the development of the Health Monitoring Unit legislation. |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  | We are planning to improve the injury data collection, thus the analysis will be more accurate and IR calculations will be correct. |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 9 |  |  |
| Summary Implementation Assessment |  |  | Excellent and sustainable system. Desired is an additional FDS reference hospital. Between 2015-2017, FDS data collection has been given up, but quality of MDS based rates has improved. Future participation in the EU IDB data exchange is very likely. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  | Nicosia, October 2017 |  |  | Maria Athanasiadou |  |  |  |  | yes |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | yes |  |

National IDB Implementation Score Card Report

Country: CZECH REPUBLIC

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 0 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 0 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 0 |  | No response since 2016 |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 2 |  |  |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 1 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 0 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 0 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 0 |  |  |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  | No data delivery since 2013 |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 5 |  |  |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 0 |  | Only children 0-18 |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 0 |  | Only admissions |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 0 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 0 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 12 |  |  |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 2 |  | New injury surveillance system to cover all age groups, but only admissions |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 0 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 7 |  |  |
| Summary Implementation Assessment |  |  | Excellent and sustainable system, but restricted to children 0-18a. Desired is the extension to other age-groups and provision of rates. Between 2015-2017, national legislation on an injury surveillance system for admissions was introduced. However, sharing of data has stopped. Future participation in the EU IDB data exchange is unlikely without governmental support. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  | Brno, October 2017 |  |  | Ladislav Planka |  |  |  |  | Informed, no objection, no explicit consent |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | yes |  |

National IDB Implementation Score Card Report

Country: DENMARK

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 2 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 2 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 12 |  |  |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 1 |  | Collection is certain, but delivery uncertain due to data protection issues (see D) |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  | FDS not yet available |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 17 |  |  |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 2 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 1 |  | Delivery is uncertain due to data protection issues |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  | Uncertain |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 8 |  |  |
| Summary Implementation Assessment |  |  | Excellent & sustainable system. Between 2015-2017, increasing challenges to maintain the FDS data collection and to secure resources for data handling. Future participation in the EU IDB data exchange is likely. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  | Copenhagen, 10.10.17 |  |  | Bjarne Laursen |  |  |  |  | OK |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: ESTONIA

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 2 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 2 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 12 |  |  |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  | Full coverage of cases |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 18 |  |  |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 2 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 9 |  |  |
| Summary Implementation Assessment |  |  | Excellent & sustainable system. Desired is an additional FDS reference hospital. Between 2015-2017, the system has been stabilized. Future participation in the EU IDB data exchange is very likely. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  | Tallinn, October 2017 |  |  | Liisi Panov |  |  |  |  | yes |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | yes |  |

National IDB Implementation Score Card Report

Country: FINLAND

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 1 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 1 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 6 |  |  |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 1 |  | Data for 2016 expected, but not yet available |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 1 |  | Data for 2016 expected, but not yet available |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 2 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 10 |  |  |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 18 |  |  |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 1 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 2 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 1 |  | Unclear interest in future EU injury data exchange |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 8 |  |  |
| Summary Implementation Assessment |  |  | Excellent & sustainable system. Desired improvements are the correction of the HD bias and one additional FDS reference hospital. Between 2015-2017, no substantial changes have taken place. Data delivery for 2016 is not completed yet. Future participation in the EU IDB exchange is not secured. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  | Helsinki, October 2017 |  |  | Anne Lounamaa |  |  |  |  | Informed, no objection, no explicit consent |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | yes |  |

National IDB Implementation Score Card Report

Country: GERMANY/ BRANDENBURG

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  | At state level, but not at federal level |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  | No metadata for 2016 yet |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 1 |  | No rates for 2016 yet |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 2 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 0 |  | Just one hospital, bias toward admissions, rates valid only for state of Brandenburg |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 2 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 11 |  |  |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 1 |  | Ambulatory treatments collected only one day per week. |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  | Rates delivered in tables, no file for automatic calculation |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 1 |  | Valid for state of Brandenburg |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 0 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 16 |  |  |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 1 |  | Second reference hospital expected |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 0 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 6 |  |  |
| Summary Implementation Assessment |  |  | Sustainable system of the state of Brandenburg. The sample of just one hospital is hardly sufficient, and automatic calculation of rates is not possible due to underreporting of ambulatory treatments. Additional hospitals & MDS collected for all treatments in reference hospitals are desired. Between 2015-2017, no substantial changes have taken place, no expansion to other federal states in Germany. Future participation in the EU IDB data exchange is very likely. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  | Potsdam, October 2017 |  |  | Gabriele Elsäßer |  |  |  |  | Informed, no objection, no explicit consent |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | yes |  |

National IDB Implementation Score Card Report

Country: GREECE

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 1 |  | Just one year during JAMIE project |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 0 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 0 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 0 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 1 |  | Collaboration stopped after JAMIE |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | 0 |  | Comments |
| - Data delivered in past five years (2012-2016) | 0 |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 1 |  | Just 2012 |
| - MDS data 2016 delivered | 1 |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 0 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  | 2012 |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 0 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 0 |  | Not applicable |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 0 |  | Small and biased sample, no rates |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 3 |  | Data collection terminated |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 0 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 0 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 0 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 0 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 0 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 0 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 0 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 0 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 0 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 0 |  | There is no system in place |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 0 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 0 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 0 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 0 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 0 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 0 |  | Search for interested partner not yet successful. |
| Summary Implementation Assessment |  |  | A successful pilot in 2012 discontinued due to lack of resources as a consequence of the financial crisis. During 2015-2017, no (other) capable national partner could not be identified. Participation in the EU IDB data exchange in the near future is unlikely. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  |  |  |  | Not available |  |  |  |  |  |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | yes |  |

National IDB Implementation Score Card Report

Country: HUNGARY

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 1 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 7 |  |  |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 1 |  | Just 2013 |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 0 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 0 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 0 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 0 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 1 |  | Sample too small, no rates |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 2 |  |  |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 0 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 0 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 0 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 0 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 0 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 0 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 0 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 0 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 0 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 0 |  | There is no system in place |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 0 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 1 |  | Legislation under consideration |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 1 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 1 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 4 |  |  |
| Summary Implementation Assessment |  |  | Successful pilot in 2013 not continued after the end of the JAMIE project. During 2015-2017, no substantial changes have taken place; efforts for a compulsory legal basis did not materialize. Participation in the EU IDB data exchange in the near future is unlikely despite of stable interest of the national partner. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  | Budapest, 13 Oct 2017 |  |  | Peter Csizmadia |  |  |  |  | OK |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: IRELAND

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 0 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 6 |  |  |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 1 |  | Last delivery 2014 |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 1 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 1 |  | Unclear |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 1 |  | Only age-group 16+ (no children) |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 8 |  |  |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 1 |  | Data collected, but delivery for 2015+ uncertain |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 0 |  | No children |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 1 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 1 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 0 |  | Just one hospital |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 11 |  |  |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 1 |  | Not secured |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 1 |  | NDA strives for MoH support |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 1 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 6 |  |  |
| Summary Implementation Assessment |  |  | Sustained but not secured system. Major shortcomings are: just one reference hospital; scope restricted to adolescents & adults (no children 0-15a). Between 2015-2017 increasing difficulties to get data from the reference hospital and to secure resources for data handling. Data delivery for 2015 and 2016 not completed yet. Future participation in the EU IDB data exchange is not secured, despite of stable interest of the national partner. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  | Cork, October 2017 |  |  | Eve Griffin |  |  |  |  | yes |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | yes |  |

National IDB Implementation Score Card Report

Country: ICELAND

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 1 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 0 |  | Support only for JAMIE project |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 0 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 3 |  | Collaboration stopped after JAMIE project |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  | Last delivery 2013 |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 0 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 1 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 1 |  | unclear |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 1 |  | Road traffic injuries not identifiable |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 7 |  | Last delivery 2013 |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 1 |  | Data available, but not submitted |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 1 |  | No road accidents identifiable |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 1 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 1 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 14 |  | Data available, but not submitted |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 1 |  | unclear |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 0 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 1 |  | For collection yes, but not for exchange |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 0 |  | Currently no resources |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 1 |  | unclear |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 3 |  | Future collaboration uncertain |
| Summary Implementation Assessment |  |  | MDS data at national level available, but collaboration with EU IDB suspended after the end of the JAMIE project. During 2015-2017, the re-start of data delivery could not be achieved. Future participation in the EU IDB data exchange is unlikely. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  |  |  |  | Not available |  |  |  |  |  |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | yes |  |

National IDB Implementation Score Card Report

Country: ITALY

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  | Last delivery: Data 2013 |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 1 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  | 2013 |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 1 |  | 2012 |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 1 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 1 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 10 |  | Last delivery: Data 2013, rates 2012 |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 1 |  | 2012 |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  | Complete regions for MDS data |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 19 |  |  |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 2 |  | Delivery of outstanding data planned for this year |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  | Legal basis for FDS |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 9 |  |  |
| Summary Implementation Assessment |  |  | Excellent und sustained implementation. Main shortcoming is the repeated delay of data delivery due to lack of resources. During 2015-2017, a solid MDS data system for estimating national rates could be established, beside the existing FDS data system. Data delivery for 2014-2016 is not completed yet. Future participation in the EU IDB data exchange is very likely. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  | Rome, October |  |  | Alessio Pitidis |  |  |  |  | Informed, no objection, no explicit consent |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | yes |  |

National IDB Implementation Score Card Report

Country: LITHUANIA

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 1 |  | 18.1% (2016) |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 2 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 1 |  | unclear |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 10 |  |  |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 18 |  |  |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 2 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 9 |  |  |
| Summary Implementation Assessment |  |  | Excellent and sustainable system. Recommended is an additional FDS data sample from at least one reference hospital. During 2015-2017, non substantial changes have taken place. Future participation in the EU IDB data exchange is very likely. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  | Vilnius, October 2017 |  |  | Rita Gaidelyte |  |  |  |  | OK |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | yes |  |

National IDB Implementation Score Card Report

Country: LUXEMBOURG

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 2 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 2 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 2 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 14 |  |  |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 20 |  |  |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 2 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 2 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 10 |  |  |
| Summary Implementation Assessment |  |  | Excellent and sustainable system. During 2015-2017, no substantial changes have taken place. Future participation in the EU IDB data exchange is very likely. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  | Luxembourg, October 2017 |  |  | Dritan Bejko |  |  |  |  | yes |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | yes |  |

National IDB Implementation Score Card Report

Country: LATVIA

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 1 |  | Slightly above 10% (2016) |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 2 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 1 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 1 |  | Almost 100% admissions |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 2 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 11 |  |  |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 1 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 19 |  |  |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 2 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 9 |  |  |
| Summary Implementation Assessment |  |  | Excellent and sustainable system. Major shortcomings: Underreporting of ambulatory treated cases; lack of an FDS data sample. During 2015-2017, no substantial changes have taken place. Future participation in the EU IDB data exchange is very likely. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  | Riga, 16.10.2017 |  |  | Jana Lepiksone |  |  |  |  | OK |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | OK |  |

National IDB Implementation Score Card Report

Country: MALTA

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 1 |  | Last delivery 2014 |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 1 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 1 |  | Last rate for 2013 |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 1 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 2 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 10 |  | Data collected, but processing is a challenge |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 20 |  |  |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 2 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 1 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 8 |  |  |
| Summary Implementation Assessment |  |  | Excellent and sustainable system. During 2015-2017, full coverage of all hospital ED patients could be achieved. Data delivery for 2015 and 2016 is not completed yet due to scarce capacities for data handling. Future participation in the EU IDB data exchange is likely. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  | La Valetta, October 2017 |  |  | Audrey Galea |  |  |  |  | Informed, no objection, no explicit consent |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | yes |  |

National IDB Implementation Score Card Report

Country: NETHERLANDS

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 2 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 2 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 2 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 14 |  |  |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 20 |  |  |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 2 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 2 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 10 |  |  |
| Summary Implementation Assessment |  |  | Excellent and sustainable system. During 2015-2017, no substantial changes have taken place. Future participation in the EU IDB data exchange is very likely. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  | Amsterdam, October 2017 |  |  | Huib Valkenberg |  |  |  |  | Informed, no objection, no explicit consent |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | yes |  |

National IDB Implementation Score Card Report

Country: NORWAY

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 1 |  | Delayed |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  | 2015 |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 2 |  | 2015 |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 1 |  | unclear |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 10 |  |  |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 18 |  |  |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 2 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 9 |  |  |
| Summary Implementation Assessment |  |  | Excellent and sustainable system. Desired is an additional FDS sample from at least one reference hospital. During 2015-2017, no substantial changes have taken place. Data delivery for 2016 has not been completed yet due to scarce capacities for data handling. Future participation in the EU IDB data exchange is very likely. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  | Oslo, October 2017 |  |  | Johan Lund |  |  |  |  | yes |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | yes |  |

National IDB Implementation Score Card Report

Country: POLAND

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 1 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 0 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 0 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 0 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 1 |  | Collaboration stopped after JAMIE |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 1 |  | Just 2013/2014 |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 0 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 0 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 1 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 1 |  | Just children |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 5 |  | Data collection stopped after JAMIE |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 0 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 0 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 0 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 0 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 0 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 0 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 0 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 0 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 0 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 0 |  | No system in place |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 0 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 0 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 0 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 0 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 0 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 0 |  | No interested partner identified |
| Summary Implementation Assessment |  |  | A successful pilot data collection in 2013/2014 stopped after the end of the JAMIE project. During 2015-2017, restart could not be achieved and no interested partner with governmental support could be identified. Participation in the EU IDB data exchange is unlikely for the near future. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  |  |  |  | Not available |  |  |  |  |  |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | yes |  |

National IDB Implementation Score Card Report

Country: PORTUGAL

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 1 |  | 20.5% in 2016 |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 2 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 2 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 1 |  | Only home & leisure accidents |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 2 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 12 |  |  |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 1 |  | Only home & leisure accidents |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 0 |  | object, second injury, type of sport not implemented |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 1 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 1 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 1 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 14 |  |  |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 1 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 1 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 7 |  |  |
| Summary Implementation Assessment |  |  | Sustainable system. Major shortcomings: Restriction to home & leisure accidents; incomplete implementation of FDS codes. During 2015-2017, the sample could be enlarged and stabilized. Future participation in the EU IDB data exchange is very likely. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  | Lisbon, 10 October 2017 |  |  | Tatiana Alves |  |  |  |  | Yes |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | yes |  |

National IDB Implementation Score Card Report

Country: ROMANIA

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 1 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 0 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 5 |  |  |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 1 |  | 2013 |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 0 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  | 2013 |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 1 |  | 2012 |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 1 |  | unclear |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 7 |  | Data collection stopped after JAMIE |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 0 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 0 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 0 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 0 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 0 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 0 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 0 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 0 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 0 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 0 |  | There is no system in place |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 0 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 0 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 0 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 0 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 1 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 1 |  |  |
| Summary Implementation Assessment |  |  | Successful pilot in 4 hospitals in one region in 2012/2013 did not lead to a permanent implementation. During 2015-2017, the pilot partner remains interested, but neither national funding nor governmental support could be achieved. Continuing participation in the EU IDB data exchange is likely, but data delivery is unlikely in the near future. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  | Cluj-Napoca |  |  | Diana Dulf |  |  |  |  | Informed, no objection, no explicit consent |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | yes |  |

National IDB Implementation Score Card Report

Country: SWEDEN

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 1 |  | delayed |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 2 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 2 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 2 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 13 |  |  |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 1 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 1 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 1 |  | 2017 only 4 hospitals, |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 17 |  |  |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 2 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 1 |  | In this moment not secured due to data protection concerns. |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 2 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 9 |  |  |
| Summary Implementation Assessment |  |  | Excellent and sustainable system. In 2018 the national coding system will be replaced by the IDB-FDS coding system. Data delivery 2016 has not been completed yet due to unsolved data protection questions. Future participation in the EU IDB data exchange is not secured due to legal issues. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  | Stockholm, October 2017 |  |  | Pernilla Fagerström |  |  |  |  | yes |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | yes |  |

National IDB Implementation Score Card Report

Country: SLOVENIA

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 2 |  |  |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 1 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 2 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 13 |  |  |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  | “All hospitals” refer to sample hospitals. |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 2 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 20 |  |  |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 2 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 9 |  |  |
| Summary Implementation Assessment |  |  | Excellent and sustainable system. During 2015-2017, no substantial changes have taken place. Future participation in the EU IDB data exchange is very likely. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  | Ljubljana, October 2017 |  |  | Tina Zupanic |  |  |  |  | yes |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | yes |  |

National IDB Implementation Score Card Report

Country: SPAIN

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 1 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 1 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 6 |  | Change of NDA organisation |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 1 |  | 2013 |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 0 |  |  |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  | 2013 |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 1 |  | 2013 |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 1 |  | unclear |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 7 |  | Data collection stopped after JAMIE |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 1 |  | Shift to new partner (Catalonia) |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  | 2013 |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  | 2013 |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  | 2013 |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 1 |  |  |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 1 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 1 |  | 2013, region of Navarra |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 1 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 1 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 12 |  | Currently no system in place |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 1 |  | Data collection ongoing in Catalonia |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 1 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 1 |  |  |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 2 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 5 |  | Catalonia intends to deliver in the future |
| Summary Implementation Assessment |  |  | Successful pilot in 2013 in region Navarra did not lead to sustained implementation. During 2015-2017, collaboration with a new capable partner in Catalonia established, however data delivery not expected before 2018. Future participation in the EU IDB data exchange is likely. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  | Barcelona, October 2017 |  |  | Catherine Pérez |  |  |  |  | Informed, no objection, no explicit consent |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | yes |  |

National IDB Implementation Score Card Report

Country: TURKEY

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  | yes |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  | Yes |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 2 |  | Yes |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  | Yes |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 8 |  |  |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  | Yes |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 2 |  | Yes |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 1 |  | Yes |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 2 |  | Yes |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 1 |  | Yes |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  | Yes |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 2 |  | Yes |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 12 |  |  |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  | Yes |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  | Yes |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  | Yes |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  | Yes |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 2 |  | Yes |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 1 |  | Yes |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  | Yes |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 1 |  | Yes |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  | Yes |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 2 |  | Yes |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 18 |  |  |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  | Yes |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 2 |  | Yes |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 1 |  | Yes |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  | Yes |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 1 |  | Yes |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 7 |  |  |
| Summary Implementation Assessment |  |  | Excellent and sustainable system. During 2015-2017, no substantial changes have taken place. Data delivery 2015 not yet completed. Future participation in the EU IDB data exchange is likely. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  | Ankara, October 2017 |  |  | Banu Ekinci |  |  |  |  | Yes |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | yes |  |

National IDB Implementation Score Card Report

Country: UK

October 2017

| A. Participation in EU-data exchange |  |  |  |  |  |  |  |  | Score |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Membership as observer or full member NDA-network | not yet |  | 0 | just since start of BRIDGE-HEALTH (2015) |  | 1 | already before BRIDGE-HEALTH | 2 | 2 |  |  |
| - Participation level in past five years | 2 or less of the eight meetings attended |  | 0 | 3-4 of the meetings attended |  | 1 | at least 5 meetings attended | 2 | 2 |  |  |
| - Government endorsement perspective for NDA-participation | No or only weak support |  | 0 | only for duration of BRIDGE-HEALTH |  | 1 | for longer term endorsement | 2 | 1 |  |  |
| - Responsive to information requests of NDA-coordinator | only after many reminders/calls |  | 0 | after 1 or 2 reminders |  | 1 | within deadline | 2 | 2 |  |  |
| A. Total score (max. 8) |  |  |  |  |  |  |  |  | 7 |  |  |
| B. Data delivery (up to 2016) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data delivered in past five years (2012-2016) | none |  | 0 | data delivered for just one year |  | 1 | data delivered for two or more years | 2 | 2 |  |  |
| - MDS data 2016 delivered | Not available |  | 0 | Not yet but expected |  | 1 | complete and in time | 2 | 1 |  | 2016 delayed |
| - Accuracy of coding (most current delivery) | more than 40% unknown |  | 0 | between 10% and 40% unknown |  | 1 | less than 10% unknown | 2 | 2 |  |  |
| - Incidence rate | Not available |  | 0 | Only on paper or not for last delivery |  | 1 | Reference population file for 2016 | 2 | 1 |  | 2015 |
| - Consistency of case definition (IDB & HDR or EDR) | IR not available |  | 0 | not consistent or unclear |  | 1 | Consistent | 2 | 2 |  |  |
| - Scope of data collection | Two or more “warning flags” |  |  | Just one “warning flag” |  |  | No “warning flag” | 2 | 2 |  |  |
| - FDS sample 2016 | Not available |  | 0 | Not yet but expected |  | 1 | Complete and in time | 2 | 0 |  |  |
| B. Total score (max. 14) |  |  |  |  |  |  |  |  | 10 |  | 2016 not yet available |
| C. Current system in place (2017) |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Data collection ongoing | no data & no plan to (re)start |  | 0 | no data but restart planned / data delivery uncertain |  | 1 | Collected & delivery certain | 2 | 2 |  |  |
| - Age groups | not covering the full age-span |  | 0 | All ages in most of the hospitals |  | 1 | all ages in all hospitals | 2 | 2 |  |  |
| - Injury categories | less than ECHI-29 |  | 0 | At least home, leisure & school |  | 1 | all injuries | 2 | 2 |  |  |
| - Outpatients | none or strongly biased toward HD |  | 0 | biased toward HD but corrected for IR |  | 1 | All HDs + all EDs | 2 | 2 |  |  |
| - Completeness of coding (mechanism, injury type, body part) | more than 1 code missing |  | 0 | just one missing |  | 1 | all codes implemented | 2 | 0 |  | Several codes (e.g. mechanism fall, location road) not implemented |
| - Incidence rates | IR not available |  | 0 | only crude rate or based on catchment |  | 1 | standardized for age and sex | 2 | 2 |  |  |
| - Geo-coverage | IR not available |  | 0 | Valid only for a region |  | 1 | Valid at national level | 2 | 2 |  |  |
| - Sampling of hospitals | Just by availability of hospitals |  | 0 | rational sampling but no validation check |  | 1 | Validated sample | 2 | 1 |  |  |
| - Hospital sample size | none or below advised minimum |  | 0 | Hardly above advised minimum (Table 4.1) |  | 1 | well above advised minimum (Table 4.1) | 2 | 2 |  |  |
| - FDS data | none |  | 0 | Sample below minimum expected (<3000) |  | 1 | Sample above minimum expected (3000+) | 2 | 0 |  |  |
| C. Total score (max. 20) |  |  |  |  |  |  |  |  | 15 |  |  |
| D. Prospects for 2018+ |  |  |  |  |  |  |  |  | Score |  | Comments |
| - Will the MDS data collection continue in 2018? | no |  | 0 | Not secured yet |  | 1 | yes | 2 | 2 |  |  |
| - Improvement or maintenance plan in place for next years? | None or just draft |  | 0 | in consultation |  | 1 | Yes or no substantial improvements necessary | 2 | 1 |  |  |
| - Legal basis for MDS data collection? | No plans |  | 0 | Ongoing substantial discussion |  | 1 | In place or very likely | 2 | 2 |  | In Wales yes |
| - Capacities in your organization for injury data collection/ analysis? | Will be reduced |  | 0 | Scarce but stay the same |  | 1 | Sufficient or will increase | 2 | 1 |  |  |
| - Interest to participate in future EU injury information projects? | no |  | 0 | Yes, but depending on availability of internal resources |  | 1 | Yes, we remain strongly interested | 2 | 1 |  |  |
| D. Total score (max. 10) |  |  |  |  |  |  |  |  | 7 |  | Brexit could affect future collaboration |
| Summary Implementation Assessment |  |  | Very good and sustained system. Desired is the implementation of all MDS codes and an additional FDS sample from at least one reference hospital. During 2015-2017, quality of the MDS based rates has been improved. Future participation in the EU IDB data exchange is uncertain due to current political developments and increasing data protection concerns. |  |  |  |  |  |  |  |  |
| Approval |  |  |  |  |  |  |  |  |  |  |  |
| Function |  | Place, date |  |  | Name |  |  |  |  | OK |  |
| National IDB data administrator |  | Swansea, October |  |  | Ronan Lyons |  |  |  |  | Informed, no objection, no explicit consent |  |
| BRIDGE-Health IDB |  | Vienna, October 2017 |  |  | Rupert Kisser |  |  |  |  | yes |  |

Annex 3: IDB implementation reports (from EuroSafe Alert) for 22 countries:

Austria, Cyprus, Denmark, Estonia, Finland, Germany, Hungary, Ireland, Italy, Latvia, Lithuania, Luxembourg, Malta, Netherlands, Norway, Portugal, Romania, Slovenia, Spain, Sweden, Turkey, United Kingdom

Country update on Injury Surveillance: Austria

Introduction

In 1987, the former Austrian Institute for Home and Leisure Safety was founded as a branch of the Austrian Road Safety Board (KFV). At the time, there were no national statistics on injuries at home and in leisure time activities. As a consequence, frequency, severity and causation of important groups of injuries (e.g. child injuries at home, falls on public roads, accidents while housekeeping, or injuries due to playing football) were unknown, and rational priority setting in prevention was hardly possible. 
Therefore, the first injury prevention programmes in Austria had to rely on data from Switzerland, United Kingdom and the Netherlands, where national injury surveillance systems were already in place.

National IDB-system

When Austria joined the European Union in 1995, the Austrian government and KFV took the opportunity to join the already existing European Home and Leisure Accident Surveillance System (EHLASS). In 1996, a sustained hospital (ED) based surveillance system was established in six hospitals in Austria.

Since this year, the system (“IDB-Austria”) provided about 10.000 detailed described injury cases annually (admissions as well as out-patients, accidents as well as self-harm and assaults) and has been funded by the Federal Ministry of Labour, Social Affairs and Consumer Protection. The Austrian system is based on face-to-face interviews with follow-up injury patients in the ED by specially trained KFV staff.

# Insights gained

With this wealth of information, it was possible since 1996 to produce:

- Annual reports on home, leisure and sport injuries, their health and economic burden, and the main characteristics of this group of health damages, which is responsible for about eight percent of all health expenditures in Austria.

- Annual national estimates of diverse categories of injuries, e.g. collisions during downhill skiing, scalds of children, injuries in kitchens, falls of elderly on stairs, bicycle accidents on public roads.

- Detailed case descriptions to develop typologies of the causation of specific injury groups, based on the co-variation of the various external and personal factors, which helped for instance to revise industrial standards for cigarette lighters, mini-scooters, and slip-resistance of floor coverings.

- Risk factor analyses and evaluation studies about the effect of specific campaigns (e.g. bicycle helmet, baby walkers) at rather low costs.

Use of data

KFV has been collecting IDB Austria data since 1996 with the main purpose of facilitating evidence based injury prevention. KFV issues weekly press releases on a wide range of injury topics to inform the public about risks and prevention measures (most of them related to the IDB). In turn, the media and injury prevention stakeholders regularly request IDB data. Various KFV research projects rely on IDB data and the annual IDB Austria report is available to the product safety stakeholders on the website of the Federal Ministry of Labour, Social Affairs and Consumer Protection. Another important IDB costumer in Austria is the safe community initiative Sicheres Vorarlberg (www.sicheresvorarlberg.at) which has commissioned two big IDB in depth programmes in the last years, one on winter sports and an ongoing one on summer sports.

Future outlook

In 2016, the scope of the IDB Austria data system has been nearly doubled, covering now ten hospitals across the country and aiming at about 18.000 interviews per year for the IDB full dataset.

New research areas that KFV is particularly interested in are health impacts of road crashes (e.g. serious injuries and long-term consequences) and under-reporting of injuries of vulnerable road users. The IDB input to both topics is currently being discussed in a Horizon 2020 project on traffic safety named SafetyCube (http://www.safetycube-project.eu/).

More information:

robert.bauer@kfv.at

IDB-related publications:

Injury Database Austria. Jahresbericht 2015. https://www.sozialministerium.at/cms/site/attachments/8/8/7/CH3434/CMS1484229858045/idb_austria_jahresbericht_2015.pdf

Five years of mandatory bicycle helmets for children in Austria – a post hoc evaluation. http://injuryprevention.bmj.com/content/22/Suppl_2

Ursachen und Risikofaktoren von Verletzungen im Skiurlaub., Deutsche Zeitschrift für Sportmedizin, 64. Jg., Nr. 2, 2013, S. 52-56.

Ursachen und Einflussfaktoren von Personenkollisionen auf der Skipiste., Sportverletzung-Sportschaden, Vol. 27, Nr. 2, 2013, S. 100-104.

Accidents and injuries in the EU. Results of the EuroSafe Reports. Bundesgesundheitsblatt Gesundheitsforschung Gesundheitsschutz. 2014 Jun; 57(6): 673-80. doi: 10.1007/s00103-014-1969-5

Schifahren und Snowboarden in Vorarlberg. Unfallerhebung Wintersaison 2011/2012., Kuratorium für Verkehrssicherheit, September 2012, 70 S.

Das Unfallrisiko auf Fußwegen in Österreich: http://www.bmvit.gv.at/bmvit/verkehr/straße/sicherheit/fonds/vsf/downloads/02endberichtunfallrisiko auffusswegen.pdf

KFV IDB Austria online access:http://unfallstatistik.kfv.at/index.php?id=58

KFV online access to IDB Austria related press releases: http://www.kfv.at/presse/presseaussendungen/

Country update on Injury Surveillance: Cyprus

Introduction

Cyprus’ participation in the EU Injury Database project began in 2006, through the Medical and Public Health Services of the Ministry of Health in close cooperation with the Health Monitoring Unit.

The IDB full data set was introduced in the Emergency Departments of two General Hospitals. Nicosia General Hospital covers the urban and wider rural area of the biggest district. The Ammochostos Hospital covers a seaside tourist area. The aim was to collect a representative sample of all injuries in Cyprus.

Due to the fact that the FDS in operation did not provide a sufficiently large and representative sample at country level, the MDS (Minimum Dataset) was introduced in 2013 until now, in five public hospitals (Limassol General Hospital, Larnaca General Hospital, Pafos General Hospital, Polis Rural Hospital and Kyperounta Rural Hospital).

Reasons for being concerned

In Cyprus, injuries due to accidents and violence are a major public health problem. They cause a large share of morbidity, long term disability and mortality. They affect the young, the economically active and the elderly. In a population of around 850.000, on average about 310 people die due to external causes of morbidity and mortality of which about 253 are due to an accident. Of these, about 98 are due to transport accidents, 26 due to accidental falls, 21 due to drowning and accidental submersion and about 10 due to accidental poisoning. About 31 people commit a suicide, and about 13 die in each year as a result of assault.

More recent data indicate the importance of prevention actions regarding accidents and injuries in Cyprus. 136 deaths due to accidental injuries could be prevented in 2015 by public health interventions. Similarly 39 and 66 deaths due to suicide and transport accidents accordingly could be avoided.

Many of these fatal injuries may be prevented by targeted measures. Such measures include strict enforcement of the law on the use of seat belts, helmets and car seats for children, applying regular checks for speed and alcohol limits, constructing safer roads, as well as placing warning signs around water areas and use smoke detection devices.

Measures to prevent falls among elderly, such as early diagnosis and treatment of depression and commercial restrictions on products identified as potential causes of accidents, are also cost effective measures that have significant potential of reducing the occurrence of injuries.

Methodology

Since 2012 we were using the IDB full data set and the IDB software for coding and data entry. From 2013 onwards the IDB Minimum Data Set (MDS) is in use. Every Emergency Department has a trained clerk who interviews the patients or relatives, collects and codes the information on a data collection form, and then enters the data into the software.

The responsibility of data analysis, quality checks on coding and reporting lies with the Health Monitoring Unit.

Some results

By analyzing the most recent data derived by the IDB Minimum Data Set for the period 2013-2016 the most common mechanisms of injury among all non-fatal injuries were falls (40.3%), road traffic injuries (18.6%) and cut/pierce (18.1%).

Home (35.6%) and Road (22.7%) were the most relevant places of occurrence of non-fatal injuries among all ages. Significant age differences exists between the various places of occurrence.

One out of ten (10.2%) small children age 0 to 4 injured at home, in which 1036 were boys and 733 were girls. 36.2% of children age 10 to 14 tend to be injured at school. Public roads were the place of injury occurrence for about 49% of young people age 15 to 35.

The biggest proportion of injuries were accidental (unintentional, 90%). A small but not insignificant proportion of injuries were due to assault (6%) and 1% due to deliberate (intentional) self-harm.

Use of data

This type of data when properly analyzed provides valuable clues as to which groups are prone to specific types of injury such as the young, the elderly, the pedestrians and other important groups which are more likely to be injured.

It also gives information on mechanism of injury and provide clues to as to the risk factors implicated in the causation of accidents.

Data analysis can be done at national and European level. Such analysis can provide useful comparison between Cyprus and other countries.

The Cypriot health professionals and policy makers are using these data to inform national prevention policies.

More information:

MAthanasiadou@moh.gov.cy

Country update on Injury Surveillance: Germany

Introduction

For more than 10 years the Brandenburg Department of Health (former Public Health Institute) has participated in the development of the European Injury Data Base. It has been a cooperating partner in several EU projects (INTEGRIS, JAIMIE and BRIDGE) and built up an IDB network with hospitals in three different regions of Germany. The hospitals get technological and scientific support, including analyses of the data that they deliver. In return they collect freely the required IDB data.

Regional IDB-system

Since 2008 the Full Injury Database (FDS) has been implemented in four main German hospitals with pediatric wards situated in Lower Saxony (City Hospital of Delmenhorst), in Saxony (University Hospital Leipzig) and in Brandenburg (Klinikum Westbrandenburg and Carl-Thiem Klinikum).

The Brandenburg hospital CTK monitors all injured patients admitted to hospital. This data is proved to be representative for the federal state of Brandenburg and annually delivered to the European Injury Data Base.

The other three hospitals focus on injuries in children and adolescents (< 18 years) and this data is not reported to the IDB.

All four hospitals collect data based by doctors or study nurses on FDS level. FDS contains both, unintentional injuries (so called accidents) and intentional injuries (by violence and self-harm). Detailed information is documented about the injury event (location, mechanism, activity of injured person), injury diagnoses (ICD-10 code) and follow up treatment. Furthermore, the product that caused or triggered an injury is collected.

In Germany, FDS also includes the doctor‘s narrative regarding the injury event, thus providing valuable insights on how the accident occurred (see publications). The Brandenburg Health Department within the State Office for Occupational Safety, Consumer Protection and Health is responsible for quality checks on coding, data analysis and reporting on regional and European level.

Insights gained

Infants are most at risk to suffer from product related head injuries. Monitoring a total of 5,969 head injuries in under 5-year-olds in the period 2008-2014 we observed that product related head injuries peak in infants 87% (561). Using a text analysis program (SPSS) for an in depth analysis of the medical narrative we identified the following five most frequent products (all of which falls related): baby changing table, furniture (e.g. couches), beds (mostly parental), buggies/strollers and carry cots. They made up 62 % of all product related injuries in infants.

The most prevalent injury event in older refugee children treated in the Potsdam hospital April-November 2016 (n=14) was falling from bicycle (3 out of 14 cases). Apparently, refugee children have insufficient ability to ride a bicycle.

Injuries due to violence among school children from 6 to 17 years show a continuous increase with the age and peak among the 15- to 17-year-olds with a dominance among boys (around 10% of all injuries). Predominant cause is interpersonal violence.

In 2016 the IDB-Data was used as a reference in a court case. An infant (<1 year old) died, according to the mothers report, falling out of the parental bed and not because of a violent act (e.g. shaken baby syndrome). The proved injury diagnosis by autopsy was intracerebral bleeding. The IDB analysis of falls in infants out of parental beds ascertained (n=89) another injury picture without a single case of serious or fatal head injuries.

Use of data

The data is annually published via the internet: www.gesundheitsplattform.brandenburg.de. The data is a component of a bi-annual publication “Accidents, Violence and Self-harm in Children and Adolescents” edited by the German Federal Statistic Office (www.destatatis.de).

Brandenburg is certified by the WHO as a Safe Community (SafeComm) region in 2009 and 2015 (www.sicheres.brandenburg.de). The data is regularly used to identify population and environments most at risk thus providing key information to the SafeComm-Steering Committee (compiled of five ministries). The SafeComm-Committee decides on the main areas of injury prevention.

The results are also presented to the six thematic working groups (e.g. on child injuries and violence) to decide on targeted injury prevention measures and how they can be best implemented at both regional and community levels.

Hospitals utilize the data for research and to inform patients about risks and safety precautions and thus gaining a reputation as a centre of health promotion in the community (see publications). Information on fact based injury prevention for pediatricians published in various German pediatric journals.

The data is used for improving product standards by the German DIN Consumer Council and the Child Safety Working Group of ANEC (European Association for the Co-ordination of Consumer Representation in Standardisation).

Safe Kids Germany (Bundesarbeitsgemeinschaft Mehr Sicherheit für Kinder e.V.) uses the IDB data to recommend age specific injury prevention measures nationwide (e.g. campaign how to avoid injuries due to animals). The National Center for Early Family Support (NZFH) uses the data to inform young parents and caregivers how to avoid injuries in early childhood

Future outlook

Most important is to keep the process of IDB data collection, analysis and reporting ongoing and to provide stakeholders with information to fine-tune their injury prevention measures, to set up new targets or to improve product standards.

More information:

gabriele.ellsaesser@lavg.brandenburg.de

# Landesamt für Arbeitsschutz, Verbraucherschutz und Gesundheit

IDB-related publications:

- Ellsäßer G (2017) Unfälle, Gewalt, Selbstverletzung bei Kindern und Jugendlichen. Ergebnisse der amtlichen Statistik zum Verletzungsgeschehen 2014. Statistisches Bundesamt (Hrsg.), Wiesbaden, in press

- DIN Verbraucherrat (Hrsg.) (2017) Study of head injuries at home in children. http://www.din.de/de/ueber-normen-und-standards/nutzen-fuer-den-verbraucher/verbraucherrat/aktuelles/studie-zu-kopfverletzungen-bei-kindern-im-haeuslichen-bereich-230030

- Albrecht M, Ellsäßer G (2016) Unfälle im Kleinkindalter- Wie können evidenzbasierte Maßnahmen erfolgreich in der Beratung von Eltern umgesetzt werden? Pädiatrische Praxis 86/2

- Ellsäßer G, Albrecht M, Böhmann J (2016) Kinderunfälle vermeiden – eine wichtige Beratungsleistung von Kinder- und Jugendärzten, bvkj, Kinder- und Jugendarzt 47/9: 572-576

- Ellsäßer G, Gries F (2016) Product related Head Injuries in Infants and Toddlers -Starting Point for a Campaign. Injury Prevention 22 (Suppl 2): A128; 10.1136/injuryprev-2016-042156.350

- Ellsäßer G, Gries F, Vanderberghe T (2016) Bunk Beds Place of Danger. Injury Prevention 22 (Suppl 2): A82; 10.1136/injuryprev-2016-042156.225

- Ellsäßer G, Gries F, Turner S, Lyons R A, Larsen B, Rogmans W, Kisser R, Valkenberg H, Bejko D, Steiner M, Bauer R (2016) Product related Head Injuries among Infants and Toddlers in Europe– a Public Health Topic.Injury Prevention 22 (Suppl 2): A129; 10.1136/injuryprev-2016-042156.353

- Woller T, Ellsäßer G, Bühligen U, Till H (2014) Sportverletzungen im Kindes- und Jugendalter Daten der europäischen Injury Database (IDB) für die Unfallprävention, Dtsch Z Sportmed.2014;65:242-247

- Ellsäßer G, Albrecht M, Trost-Brinkhues G (2013) Unfallprävention bei kleinen Kindern – ein Thema für Frühe Hilfen? http://www.fruehehilfen.de/no_cache/serviceangebote-des-nzfh/ materialien/

publikationen/einzelansicht-publikationen/titel/datenreport-fruehe-hilfen-ausgabe-2013/

- Ellsäßer G, Erler T (2010) Die Gesichter der Opfer – Auswirkungen von Gewalt bei Kindern und Jugendlichen erkennen. Pädiat. Prax. 75: 287-395

- Geerdts L, Ellsäßer G, Führer S, Erler T (2010) Misshandlungen und Gewalt als Verletzungsursachen im Kindesalter – Ergebnisse eines Unfallmonitorings bei Kindern und Jugendlichen in Südbrandenburg (Deutschland). Der Unfallchirurg, Volume 113, Number 7, 568-572

Country update on Injury Surveillance: Denmark

History

Denmark has a long tradition of injury registration in a hospital setting. The first systematic registration was of traffic injuries at Odense Hospital in 1971. This was extended to all accidents in 1976.

In 1988, registration of Home and leisure injuries started at five hospitals as part of the European Home and leisure Accident surveillance system (EHLASS). From 1990 onwards, this registration was extended to all accidents (including road and work related accidents), and from 2008 to all injuries (by including violence and self-harm).

All these registrations are quite detailed, including information on e.g. products involved. While the registration in Odense was part of the routine registration to the national Patient register, the injury register at the five EHLASS -hospitals was run parallel to the mandatory registration to the National Patient Register.

The National Patient Register includes information on all admissions since 1977, and from 1995 onwards, it includes emergency department registrations at all Danish hospitals using a minimum data set containing data on injury mechanism, activity, place, and mode of transport and counterpart for traffic injuries. The information is obtained by interviews made by secretaries when the patient arrives, and coded afterwards. Different classifications have been used for these registrations. Therefore, the data are not always directly compatible. The classifications used are EHLASS and NOMESCO classifications of external cause of injury versions 2, 3, and 4. When introducing the version 4 of the NOMESCO classification in 2008, this classification was implemented at national level allowing for registration of both a minimum dataset and an extended dataset including e.g. products.

In 2010, the Injury register was closed and replaced by a pilot registration at three hospitals, including Odense Hospital. This registration used the extended dataset, while the minimum dataset continued to be used at all other hospitals in Denmark. Due to the lack of funding and budget cuts the pilot study was not continued and ended in 2012.

Current situation

All hospitals in Denmark record data consistent with the IDB-minimum dataset, however without the narrative. An evaluation of the pilot study in 2010-2012 recommended that all hospitals should register a minimum dataset that is much simpler than the previous data set and that should be more in line with the IDB minimum dataset. This was implemented in 2014 and resulted in reduced workload at the hospitals and improved data quality.

Only one hospital is continuing to register injury patients at a detailed level at present: the Odense University Hospital. At this hospital information on sports and products are written as text and coded automatically afterwards. Even this hospital is challenged due to changes in IT systems and the organizational structure, as well as data protection regulation, e.g. narratives cannot be processed without special permission

Use of data

The main purposes of injury registration in Denmark are surveillance and monitoring trends. Both the National Institute of Public Health and the Accident Analysis Group in Odense have published annual reports as well as study reports on injury trends. These have been used by both governmental institutions, NGOs, and the media to put injury prevention on the agenda. One of the successful intervention actions is the action on injuries due to firework – the number of injuries has been reduced significantly during the last decade. Data on traffic injuries have been used to change road crossings to become safer.

By being based on person numbers from 1995 onwards, injury registration can be linked to other register information like socioeconomics, use of medicine, type of dwelling etc. This has been used in several research projects, e.g. on risk factors for childhood injuries and long-term consequences of injury.

The main political interest in injury registration at hospitals has been in the registration of traffic injuries, because these are underreported by the police. Governmental involvement in injury registration and injury prevention for home and leisure injuries has generally been relatively low; this registration has sometimes been dealt with as a “by-product” of the registration of traffic injuries.

The most frequent user of home and leisure injury data is the Danish Safety Technology Authority, which has the responsibility of product safety; they have used the injury data to set priorities.

The National Board of Health is now beginning to set focus on injury prevention and is working on the clarification of the responsibilities between the different ministries. But still, the funding of the collection of a detailed data set from a sample of hospitals remains uncertain for the time being.

More information:

Bjarne Laursen

E-mail: bla@si-folkesundhed.dk

IDB-related publications:

Laursen B, Helweg-Larsen K: Health service use in adults 20-64 years with traumatic brain injury, spinal cord injury or pelvic fracture. A cohort study with 9-year follow-up. BMJ Open 2012 Oct 26;2(5)

Laursen B, Møller H: Long-term health effects of unintentional injuries in Danish adults. Dan Med J 59(5):A4423 (2012)

Hanne Møller, Mathilde Damm, Bjarne Laursen. Ulykker i Danmark 1990-2009. [ Injuries in Denmark 1990-2009] Statens Institut for Folkesundhed, Syddansk Universitet, 2012. [In Danish with English summary]

Toft AM, Møller H, Laursen B: The years after an injury: long-term consequences of injury on self-rated health. J Trauma 69(1):26-30 (2010)

Country update on Injury Surveillance: Estonia

Introduction

Injuries are a major public health concern in Estonia like in other EU-member states. Injury mortality rate per 100 000 inhabitants in Estonia has declined continually over the last two decades. However, it is still one of the highest in the EU, being more than two times higher than the EU average.

Injuries are the third leading cause of death in Estonia and they also cause large share of
morbidity and long term disability. There were 68 deaths per 100 000 inhabitants in Estonia in 2015, representing 6% of all death cases that year. A total of 25 years of life (Disability Adjusted Life Years, DALY) were lost per 1000 inhabitants in 2013 because of injuries, accounting for almost 7% of all DALYs. The proportion differs largely between age groups: it was largest in age group 25-34, where men lost 41% and women 14% of life years due to injuries.

Reducing injury mortality is one of the National Health Plan main spearheads. In 2013, the Government Office created a task force for injury mortality and morbidity prevention. Its aim was to analyse the current situation and prevention policy, and to offer additional targets and prevention methods to reduce injury mortality in Estonia to the level of EU average. The task force made its recommendations to the Government in the beginning of 2015, and thus ended its work.

Data collection efforts

National Institute for Health Development (NIHD) collects aggregated morbidity data annually as the basis of national health statistics. The reports include the number of new cases according to ICD-10 by patients’ age group, and the number of new cases by external causes. All Estonian health care providers are obliged to submit annual reports about all in- and out-patient injury cases to NIHD.

It is obvious that for in-depth analysis such aggregated data is not sufficient, and an individual level dataset is needed. At present, individual level data from National Insurance Fund is used for regular analysis of burden of disease. Case based data is available from Estonian e-health information system (HIS), but it is not used for regular statistics, yet. There is no stand-alone injury registry or database in Estonia, neither a hospital based injury surveillance system. One hospital in Estonia has piloted the FDS data collection but due to the lack of resources, they continued to use ICD-10 for registration of injuries.

The Estonian HIS was established in 2008. It is a nationwide database that has a standardized central information exchange function. Summaries of patients’ medical records are gathered from all healthcare service providers and stored in one central database. The main objective is to give healthcare professionals a comprehensive overview of patient’s diagnoses, prescribed medications, laboratory test results, and other health data. HIS enables patients to access their medical data through a patient portal.

This information can also be used, under strict anonymity, for statistical purposes and for research as well as for monitoring quality of treatment and for health policy planning.

Comparison with annual statistical reports shows that nearly 90% of in-patient case summaries and 75% of those of ambulatory visits done in hospitals are sent to HIS. While extracting data for IDB, the problem with ambulatory cases is that it is not known whether the visit is an emergency department (ED) attendance or not. Only ICD-10 coding is used for diagnoses, including injuries and external causes.

Use of injury data

Main users of injury data are NIHD, Ministry of Social Affairs (MoSA), Ministry of Interior, and the Road Safety Agency. Also other national and international organizations, local communities, media, students, scientists, etc. use the data. The HIS data provides valuable insights who, when and why have injuries and it helps to plan prevention policies and activities at national and community level, but it is also used for ad-hoc purposes.

Future outlook

Since 2015, MoSA is the coordinator of all actions in the field of injury prevention. For example, there is a need for target group specific preventions – one solution does not fit far all. More emphasis has to be put on accidental falls and suicides. Individual based data could be used to compile a profile of people who are prone to self-harm or commit suicide. The Government has agreed that the proposals made by the injury prevention task force will be implemented by 2020. It is also agreed that an overview of the current situation in the field on injuries has to be submitted annually to the Government.

As for comprehensive individual level data, efforts are made to encourage all health care providers to send all case summaries to HIS. It would be also helpful if we could link the case summaries with digital ambulance records.

Although it is widely recognised that using ICD-10 to code injuries does not provide sufficiently information on the causes and circumstances of injury events for prevention purposes, Estonian hospitals are not willing to implement a different coding or complementary surveillance system. Therefore, Estonia will continue to provide data for IDB as a Minimum Data Set on the basis of ED attendances, but from ALL hospitals in the country.

More information:

liisi.panov@tai.ee

IDB-related publications:

The report of injury prevention task force, 2014

https://riigikantselei.ee/sites/default/files/content-editors/uuringud/vigastuste_ennetamise_rakkeruhma_aruanne.pdf

The analysis of injuries and injury deaths in Estonia, 2014

https://goo.gl/8zSFsF

Injuries in Estonia, policy brief, 2009 (ENG)

http://rahvatervis.ut.ee/bitstream/1/1921/2/Laijt2009_inglisek.pdf

Non-fatal injuries resulting in activity limitations in Estonia: a retrospective population-based study, 2011 (summary in ENG)

http://www.academia.edu/20464907/Toimetulekupiiranguid_p%C3%B5hjustanud_vigastused_Eestis_rahvastikup%C3%B5hine_s%C3%BCndmuslooline_uuring

Injuries in Estonia, 2007

https://docs.google.com/viewer?url=http%3A%2F%2Frahvatervis.ut.ee%2Fbitstream%2F1%2F1661%2F4%2FKaasikjt2007.pdf

Country update on Injury Surveillance: Finland

Introduction

Finland first joined EU-level injury monitoring efforts in 1986, through the EHLASS (European Home and Leisure Accident Surveillance System) initiative. From 1992 to 1998 data collection was the responsibility of the Finnish Consumer Authority (since 2013: Finnish Competition & Consumer Authority) and its product-related injuries database. Since 2004 the National Institute for Health and Welfare-THL (until 2009 known as National Institute for Public Health) is acting as the national coordinating agency for injury prevention with an emphasis on home and leisure injuries.

National IDB-system

The Finnish contribution to IDB (as of 2014) in the form of the Minimum Data Set is produced by THL through random sampling of patients’ care episodes from the Care Register for Health Care (inpatients). The register’s size enables uniform and adequate representation of different hospitals, patient groups and accident types. Data in the Care register is coded in ICD-10, hence diagnostic information is re-encoded through conversion tables concerning injury type (12-category variable), accident location (road, school, home, other specified, not known), and accident mechanism. Data is gathered from the start of treatment (by year and month), including any follow-up care.

Insights gained

In Finland, unintentional injuries are the 4th leading cause of death across ages - putting injuries in a par with other major public health concerns. In 2015, 2 161 deaths were caused by injury or 4% of all deaths. Furthermore, unintentional injuries are the leading cause of death in the population between 1 and 45 years of age. Although the absolute total number of deaths by unintentional injuries falls far behind deaths caused by cardio-vascular diseases and cancers (the mainstay causes of death particularly in older age-groups), a different picture emerges when comparing years of life lost. In this approach of examining the data more weight is given to deaths in young ages.

In Finland unintentional injuries are causing the largest number of years of life lost up until the age of 50, whereby cardiovascular diseases and cancers come in the lead. As for in-hospital treatments, injuries form the diagnosis group with largest number of patients annually and, with over 100 000 care visits per year, belongs also to the top-four diagnosis group in terms of care visits. A similar trend can be seen in outpatient visits, although missing data on diagnosis makes the estimate less reliable.

Although injury-related mortality has been steadily declining for over a decade, certain population groups and injury types still require particular attention.

Falls and stumbling caused 1100 deaths in 2015, around one-half of all fatal injuries and predominant in the age group over 65. Just under one-half of stumbling accidents occurred at homes or in the immediate vicinity, and one-quarter in care institutions.

Overall alcohol-related mortality has decreased and so has the presence of intoxication in injury deaths (16% of those involved in fatal accidents in 2015 were intoxicated). Nevertheless, alcohol intoxication played a role in nearly half of sauna-related deaths, drownings and fire deaths and in 20% of fatal transport accidents.

Fatal transport accidents overall have also decreased dramatically (268 deaths in 2015, down by one third since the last decade), however they are the main cause of injury death in the under 25’s.

For the younger and middle-aged adult population, fatal poisonings (average age 40 years for men and 58 for women) and drug related deaths (most absolute numbers among 30-34 year-olds) also pose major issues.

Use of data

In Finland, national injury data and timely and reliable statistics on injuries and their costs are an essential support to national injury prevention programmes and strategies as well as to local injury prevention projects. National level preventive actions are implemented through inter-ministerial collaborations and networks with wide stakeholder representation.

In support of local level activities THL’s injury prevention staff produces since 2008 annual regional injury reports based on FINJURY, the Finnish injury research register. FINJURY includes injury mortality and morbidity data at an individual level from 1971 onwards, augmented with cost data for hospital care. Regional injury reports include figures, tables and indicators by region and municipality on fatal and non-fatal hospital treated injuries, thus supporting local injury monitoring efforts.

Future outlook

Despite the good quality of national data, there is still room for improvement. Coverage on external causes of injuries is good on hospitalisations and visits to secondary care, but in primary care, where many first contacts take place before referral to specialist treatment or e.g. in the case of sports injuries treated by physiotherapists, the registration of external causes is not mandatory.

Further, some types of information such as that arising from accident investigations and various risk data sources should be better linked with the official monitoring systems to improve understanding of the related risks of injuries.

Overall, health data collection in Finland has become fully digital since the operation of the National digital repository for electronic patient documents (Kanta) in 2013. Injury prevention specialists in THL are exploring the possibilities of progressing towards automated injury monitoring. Opportunities for richer and more timely data collection arise e.g. through the Forensic Medicine Information System which aims towards production of fully electronic death certificates, as well as through the forthcoming electronic emergency services record, part of the Multi-Agency Field Commanding System (KEJO) for all Finnish Public Protection and Disaster Relief (PPDR) authorities.

In coupling with enhanced data collection, modern dissemination practices from national data sources can also significantly improve injury prevention efforts. Incorporating injury-specific indicators in the forthcoming updated and more user-friendly reporting system of THL data and indicators is one of our next development steps.

More information:

persephone.doupi@thl.fi

IDB-related publications:

National action plan for injury prevention among children and youth:

http://urn.fi/URN:NBN:fi-fe201205085263

https://www.thl.fi/en/web/injury-prevention/accidental-injuries/statistics;

https://www.thl.fi/documents/568266/1481840/STM_2014_1_tapaturma_eng_appndx2.pdf/597f1137-b862-409d-8b23-93e390b37264

Country update on Injury Surveillance: Hungary

Introduction

As in most other countries in Europe, in Hungary a great variety of sources are providing only a very fragmented spectrum of information on injuries. For instance, hospital discharge data are providing information on severe injuries, but this information is still deficient as to the causes and circumstances of the injury event.

This was the reasons why the National Institute of Health Development (NIHD), before the National Centre for Health Care Audit and Inspection, decided to start a pilot testing the possible implementation of an injury data surveillance system in Hungary.

In 2009, a workgroup has been established in cooperation with the Ministry of Health-Department of Noncommunicable Diseases and Department of Informatics in order to collect and process injury records in accordance with the principles of the EU-Injury Data Base (IDB).

Among the members of the workgroup were a public health doctor, a medical IT expert and three IT staff members. The coordinator of the group was the head of the Department of Noncommunicable Diseases. The IDB-coding manual was translated into Hungarian language and a web form for the data collection has been developed.

Pilot results

The pilot data collection in Hungary has been conducted in the Southern Transdanubian Region, which counts a population of one million (total population of Hungary: 10 million). A total of 8 hospitals participated, most of them were smaller hospitals. The data collection took place from February 2010 to the end of May 2010. A total number of seventeen persons was actively involved in collecting the data, most of them nurses and administrators. They worked under the supervision of a medical doctor who was responsible for primary data control. Secondary data control was made by informatics.

During the pilot project a total of 12 654 cases were collected. The gender distribution favours males (7143) to females (5409). In 102 cases the gender remained unknown. In age groups from 15 to 39 the proportion of males among the injured persons is about the double as that of the females. The large difference in gender at ages 75 and up is due to the relatively higher number of elderly women (2:1) than men in the population. About 93% of the cases were reported as unintentional injury. The remaining cases are assaults (4%) and intentional self-harm (1%). In the 2% of the cases the intent was not indicated.

Almost half of the cases were identified as home and leisure accidents, the second largest group is related to sport, and these two categories compose more than two third of the total number of injuries. The highest proportion of the injuries was suffered during household activities. The largest difference between genders is in injuries related to sport and exercise, while females show a tendency to sustain injuries during vital activity.

Use of data

All types of injuries were analysed separately. Especially the police services were interested to use this data related to road traffic injuries. But also the huge number of sports and leisure related injuries attracted the interest of the medical professions and of policy makers in government.

The results were also presented at the Ministry of Health, in January 2010. Based on the outcome of this meeting, the Hungarian Ministry of Health signed a partnership agreement with EuroSafe for the Joint Action JAMIE.

Next steps

Based on the outcome of the pilot project the Hungarian Ministry of Health signed a partnership agreement with Eurosafe for the Joint Action of Monitoring Injuries in Europe (JAMIE). The National Institute for Health Development developed a data collection system and coordinated the IDB data collection for JAMIE. Between March 2013 and February 2014 3,681 cases were collected in FDS in one reference hospital whose trauma unit serves a catchment area of 577,000 residents for all type of injuries except burn and child care.

Because of the outcomes of the IDB data collection projects injury prevention got highlighted by policy-makers and professionals, so injury prevention became a solid part of all public health programmes and plans in Hungary. With the help of the IDB collected data stakeholders got more information on unintentional injuries (e.g. falls) beside traffic injuries and therefore their prevention came into view in the field of public health.

The future plan related to IDB data collection is to finish the formerly started legislative procedure, the aim of which is to make injury data collection on MDS mandatory in all trauma units. It is planned not be a new data collection system, only a rearrangement of the one that is in operation nowadays, with some new aspects. By implementing a new data collection system nurses and doctors will not have as much administrative work as they had in the pilots.

More information:

varsanyi.peter@nefi.hu

# NATIONAL INSTITUTE FOR HEALTH DEVELOPMENT (NEFI)

IDB-related publications:

https://www.ksh.hu/elef/archiv/2009/kal_benyi2.html

http://www.oszmk.hu/dokumentum/NEJ/nej2008_2.pdf

Country update on Injury Surveillance: Ireland

Background

In 2014, injury accounted for 11% of the 512,681 hospital in-patient discharges and 5% of the 29,252 registered deaths in Ireland. Annually, injury accounts for almost two-thirds of all Irish deaths in the age range 5-34 years, making it one of the most significant contributors to years of potential life lost.

The National Health Strategy (2001) acknowledged the need for a national injury prevention strategy, and identified the key groups where preventable injuries were highest, particularly young children and older adults. The strategy called for a co-ordinated approach across sectors to achieve this but, despite interest and support from key stakeholders and medical professionals, no action was taken at a national level.

One example of Irish injury prevention success relates to road safety. Ireland had an above-average rate of transport deaths, but over the past decade significant investment into successive road safety strategies has approximately halved the mortality rate. However, similar investment has not yet been made into the prevention of other injury-related deaths, and their rates have remained stable or increased.

ED-based data collection

The National Data Administrator for injury in Ireland is the National Suicide Research Foundation. The Foundation operates the National Self-Harm Registry Ireland and since 2006, has recorded self-harm presentations to all emergency departments (EDs) in the country. In 2015, 11,189 presentations were recorded, accounting for 1% of all ED presentations, yielding an incidence rate of 204 per 100,000.

The NSRF collaborated as the Irish partner in the Joint Action on Injury Monitoring in Europe (JAMIE), 2011-2015, and has contributed data to IDB previously. A surveillance system was implemented, on a sample basis, in the three hospital EDs in Cork City over a 6-month period in 2005. The 2,957 recorded injury presentations gave a total injury rate of 11,322 per 100,000. The peak male rate was among 15-29 year-olds, 2.5 times the female rate for the same age range. In women, the peak rate was recorded among over 85 year olds.

The findings, if generalised to Ireland as a whole, suggested that 45% of the 1.2 million presentations to Irish EDs annually are due to injuries. However for a high proportion of cases information on many of the core data items, such as activity and location when injured, was not available.

Current data collection

The primary objective of the JAMIE project in Ireland was to pilot the development and implementation of a hospital-based injury monitoring system. The project involved assessing current hospital data collection practices and procedures and identifying suitable hospital EDs for injury surveillance. An additional aim was to extrapolate incidence rates of injuries among the general population as well as assessing the burden of injuries in the country. Activities in the project have involved identifying and contacting key stakeholders and assessing hospitals for participation in the project. From the hospitals that have been surveyed, none have ED information systems capable of providing the data for FDS injury surveillance systems, with only a minority capable of providing data for MDS injury data. Arising from the JAMIE project, MDS data collection commenced in one large hospital ED in Dublin. Since 2013, data on all injury presentations for adults only (16+years) have been collected. At present, the activities of the NSRF as NDA for Ireland are being supported by the European BRIDGE-Health Project (2015-2018).

Future outlook

It is planned to continue to MDS data in Ireland for adult presentations and to expand the coverage to child and adolescent attendances for the collection of 2015 data. However, there is currently no funding to support such data collection on an ongoing basis or to support dissemination activities.

More information:

evegriffin@ucc.ie

SINIACA: a systemic approach to the national surveillance of home injures

► Country update on Injury Surveillance:

Italy

SINIACA: a systemic approach to the national surveillance of home injures

► Country update on Injury Surveillance:

Italy

Every year about 3 million 2 hundred thousands Italians suffer home injuries. Among the injured, around 1.7. million of them ask for assistance of Emergency Departments (ED) and about 125,000 are hospitalized and 5,500 die for this reason. Important results have been achieved in the last decade in terms of reduction of mortality and morbidity incidence for every type of unintentional or intentional injury. Nevertheless home, leisure and sport injuries still remain the least affected domains of injures by the aforesaid incidence reductions. Therefore the prevention of this typology of events represents an objective priority of public health and the availability of a suitable surveillance system is of fundamental importance for evidence based prevention.

In consideration of these aspects and in enforcement of the Law 493/99 a national information system on the home injuries (SINIACA) has been activated at the Italian National Institute of Health (ISS). The system is structured onto three levels of information:

- Mortality database;

- Hospital Discharge Register (HDR);

- ED sample surveillance.

The first two levels are accomplished by using current mortality and HDR data. At the third level ED surveillance of home accidents have been implemented in a sample of more than 20 hospitals all over the nation. Their catchment area covers 3.5% of the Italian population. These hospitals use a common coding system which registers the external causes of accident (mechanism of injury, activity at the time of injury, place of occurrence) with extremely simplified code lists: not more than 15 items for each voice (i.e. “mechanism of injury”). Data conversion procedures have been developed from Italian national simplified codes to IDB “all injuries” ones. These procedures are based on heuristic algorithms and require data revision for the completion of an entire database.

In the SINIACA ED registration procedures data linkage have been established between ED and HDR records in order to follow the patient from the moment of his initial attendance at the hospital to the discharge from it.

Parallel with the national system a smaller sample of hospitals participated directly into EU-IDB. They were 9 hospitals in year 2005 registering home and leisure accidents with the EHLASS V2000 coding format. In 2010 three hospitals participated in the EU-IDB within the European INTEGRIS project registering home and road traffic accidents and intentional injuries (auto-inflicted or by aggression). The EU-IDB “all injuries” coding format was adopted in year 2010. Finally at national level a smaller sample of 8 hospitals registered road traffic accidents in a national simplified coding format for the external cause of injury.

The participation in the SINIACA ED network is voluntary and participating hospitals have rotated throughout the years, but a core of around 20 hospitals all over the nation has been assured.

The ED data are integrated with HDR ones at central level by data linkage. Current HDR and mortality data are transmitted to the SINIACA system by central agencies (Italian National Institute of Statistics and Ministry of Health) and regional epidemiologic observatories. The characterization of the external cause of accidents at sample ED level and its integration to general current statistics consent to extrapolate the results at national level. Having a complete “picture” of the burden of home accidents in Italy using the available current information and integrating it with in-depth sample surveillance on the external causes of accidents is a key element for the provision of evidence based prevention strategies. Within this framework the Italian National Institute of Health has also participated in the EU-IDB network developing procedures for making the nationally coded information comparable to the European one. A dedicated website has been developed for the dissemination of the SINIACA results at http://www.iss.it/casa/.

More information: Alessio Pitidis Dept. of Environment and Primary Prevention, Italian National Institute of Health E-mail: alessiop.dati@gmail.com

Country update on Injury Surveillance: Lithuania

Background

Lithuania is the largest country of the three Baltic states. Lithuania has an estimated population of 2.9 million as of 2015, and its capital and largest city is Vilnius. On 11 March 1990, the year before the break-up of the Soviet Union, Lithuania became the first Soviet republic to declare independence. Prior to the global financial crisis of 2007–2010, Lithuania had one of the fastest growing economies in the European Union.

Health Information Centre of Institute of Hygiene (HIC IH) is responsible for health statistics, especially causes of deaths, health care and health resources statistics. HIC IH collects data using annual survey of health establishments (health care resources and some data on health care activities) and data from administrative data source such as the Compulsory Health Insurance Fund information system (CHIF IS) managed by the National Health Insurance Fund under the Ministry of Health.

Current situation

In Lithuania there are 35 hospitals with traumatology departments at present. The Ministry of Health has a plan to reduce the number of traumatology departments to 12 trauma centres in big cities and county centres. Primary care is being provided by 2600 family physicians and other primary health care physicians (therapists and paediatricians) working in about 400 primary health care institutions. In 2015, 427146 persons had injuries or poisonings and were treated in hospitals, out-patient units and in primary health care.

The main source for morbidity statistics calculation is the Compulsory Health Insurance Fund information system (CHIF IS), which covers data on hospital discharges (about 99%), out-patient visits (90%), and primary health care visits (100%). HIC IH gets the copy of CHIF IS with recalculated personal ID numbers for statistical data calculations. Data in CHIF IS is available from 2001. During the period 2009-2011, injuries and poisonings in hospital discharge were coded by ICD-10 on 4 digits level with external cause code, since 1st June 2011 – by ICD-10-AM (Australian modification) 5 digits level with 3 codes of external causes.

Since 1st of June emergency departments (ED) started to use new expanded statistical form for out-patient with ability to register up to 3 codes coded by ICD-10-AM 5 digits level. External causes for out-patient care (incl. primary care) are coded only by 9 groups of external causes. Coding of external causes for CHIF IS is mandatory. However, the quality of coding is not very good. 11% of cases are not coded at all, unspecified codes are often used. At this moment hospitals do not have extra staff for coding injuries and this has impact for coding quality.

In 2015 CHIF IS reported 43650 hospital discharges due to injuries and poisoning (S00-T98), of which 22591 falls (51.8%), 3926 exposure to inanimate mechanical forces (9%), 2365 intentional self-harm (5.4%), 1908 transport accidents (4.4%). In addition there were 308852 episodes of out-patient care in emergency departments of hospitals.

National injury monitoring project

During the period August 2011 – September 2015, with financial support from the EU Structural Fund, Institute of Hygiene implemented national project “Injury and Accident Monitoring System”. The national project aim was to create the national system of monitoring of injuries and accidents (trauma register), including as many data as possible for health policy planning, health care administration, public health, international data collection needs. It was carried out in close collaboration with data providers and national consultative group of stakeholders, i.e. data users, in the relevant governmental departments and agencies.

The main intent of this project was to create register witch could allow comprehensive data collection on treatment of injuries as well as later stage consequences, i.e. disability. For this reason the use of personal ID was necessary for follow up the patient. But according to the Law of Personal Data Protection in order to create the register with personal ID collection this register should be defined in the Law. Unfortunately due to time limitation of the project it was not possible to change the necessary Law and the system was created without possibility to link data from different data sources. By now, data from different sources could be compared by clinical diagnosis, region, age and gender.

The Information system of Injury and Accident Monitoring was officially started in 1st of September 2015. Data on injuries from CHIF IS (treatment episodes of injuries), Causes of Death Registry, The State Social Insurance Fund Board under the Ministry of Social Security and Labour (data on sick-leaves due to injury), Disability and Working Capacity Assessment Office under the Ministry of Social Security and Labour (data on disability due to injury) are collected into this system.

The system of Injury and Accident Monitoring covers all hospitals (in-patient and emergency departments) in Lithuania. Using this system external cause data could be converted to IDB minimum data set (MDS-I) for all hospital discharges from 1st of June 2011. Since 2013 MDS-I are available for out-patients of emergency departments in hospitals as well.

In order to have Full Data Set (FDS-I) additional coding of external causes is needed. Introduction of such coding is foreseen only with the full implementation of e-health.

More information:

Neringa Madeikyte,

neringa.madeikyte@hi.lt

IDB-related publications:

http://www.hi.lt/lt/traumu-leidiniai.html

Country update on Injury Surveillance: Luxembourg

Introduction

Luxembourg was part of the “European System of Home and Leisure Accidents (EHLASS)” from tits start in 1986. The Ministry of Social Affairs, responsible of the European project at the national level, organized the data collection on home and leisure accidents in the emergency department of one hospital. The Ministry of Economics, in charge of the project from 1993 to 1999, opted, as some other European countries, for a yearly phone survey focusing on product related injuries. After 1999 the responsibility for the project was taken over by the Ministry of Health, that since then continues to be a permanent participant in the European project.

An evaluation of the EHLASS methodology that was in place from 1993 to 2000, brought up a list of recommendations for the implementation of a new national surveillance system. To inform on injury burden and feed the national injury prevention policy planning, it was decided to collect continuously information on all types of injuries from the emergency departments of the hospitals.

National IDB-system

In 2009 in collaboration with the Luxembourg’s Institute of Health, a new initiative of a national injury surveillance system was launched. A two-month pilot project started in the emergency department of one main hospital of the country using the well established european Injury Data Base (IDB) methodology.

Luxembourg is a small country with eight emergency departments in four hospitals, with an alternating 24 hour on duty system for two of those hospitals, and some specialized medical services only present in one hospital. To implement an exhaustive injury surveillance system, it was decided to collect the IDB Full Data Set in one hospital and the IDB Minimum Data Set in all other hospitals. Since 2012, Luxembourg’s data are included in the European IDB and data collection is still ongoing in three out of four hospitals.

Insights gained

In Luxembourg (576 000 inhabitants), like in the other EU countries, injuries are the 4-th cause of death in the general population and the principal cause of death among children, adolescents and adults aged 1 to 44. Out of the average injury 263 deaths a year between 2005 and 2014, 23% were suicides and 69% accidents among which 18% falls and 16% traffic injuries .

Every year for each injury death 17 peopels are admited to hospital and 230 others are treated as out patients in the emergency departments due to an injury. The yearly incidence rate is estimated 105 ‰ inhabitants but this figure is twice as high among adolescents and older people. Home and leisure accidents are the most common cause of injury.

Use of data

A first national report based on 2013 data from all the hospitals has been published in 2015 and a second is being finalized. At international level the latest edition of Injuries in the European Union is launched (November 2016). Actors active in prevention of road trafic injuries, and consumer safety are already using the data . Other actors involved in the prevention of falls among older people, familly violence, suicide have shown interest for these data. Front page articles that include results from the injury surveillance system have been published by the national press.

Future outlook

All hospitals of the country will be included in the system. Machine learning techniques are being implemented to reduce the running cost of the system by keeping the good quality of data. Data usage will be increased by involving other actors in injury prevention. Data linkage using Master Patient Index from third trusted parties will widen the potential of the system with respect to ethical requirements.

More information:

Dritan.bejko@lih.lu

IDB-related publications:

http://www.sante.public.lu/fr/publications/t/traumatisme-lux-retrace-2015/index.html

http://www.sante.public.lu/fr/publications/r/retrace-traumatismes-accidents-luxembourg-fr-de-pt-en/index.html

http://injuryprevention.bmj.com/content/22/Suppl_2/A81.2.abstract?sid=112778b2-c13b-42a2-9b5d-b17fc2608919

http://injuryprevention.bmj.com/content/22/Suppl_2/A81.3.abstract?sid=19371be3-800f-4f88-88e4-2e1979ad88a2

Country update on Injury Surveillance: Malta.

Introduction

The Maltese archipelago lies virtually at the center of the Mediterranean just 93km south of Sicily and 288km north of Africa. The archipelago consists of three islands: Malta, Gozo and Comino with a total population of just over 400,000 inhabitants over an area of 316sq km and a coastline of 197 km (not including 56 km for the island of Gozo) making Malta one of the most densely populated countries.

The Department of Health has long felt the need for injury surveillance. The main impetus came from two sources.

Firstly, our mortality records show that falls are still a substantial underlying cause of death in the Maltese elderly. The Injury database can provide an insight into such injuries – particularly the non-fatal ones, with a view to design policies and facilitate measures to reduce this cause of morbidity. Secondly, the Malta Standards Authority has been seeking to collaborate with the Department of Health on the issue of product safety surveillance, so that data would be available on injuries related to the use of consumer products or services.

Data on injuries treated in Emergency Departments provide invaluable information on the circumstances and causes of product related injuries and assist enforcement officers in their risk assessment procedures.

Malta’s Health Care System

Malta has a long history of providing publicly funded health care known as the government healthcare service, where healthcare is free at the point of delivery, in parallel to a private healthcare system. Primary care is predominantly being provided in solo private general practices (60%) and in the public district health centers (40%). Public hospitals provide most of the secondary

and tertiary care.

There are two public general hospitals in Malta. Mater Dei Hospital, inaugurated in November 2009, is Malta's primary hospital, and one of the largest, most modern and well equipped medical centers in Europe. Gozo General Hospital (GGH) is the other government hospital located on the island of Gozo.

Data from emergency departments

The Injury Data Base was officially launched in Malta in September 2004. The Department of Health Information and Research (DHIR) is the body responsible for the compilation of such data.

Data collections started at GGH, using a specific form for Malta which included the minimum data set of information in line with the EU-IDB. This was designed in such a way so as to facilitate the completion of the form by triage nurses or doctors, through minimisation of free-text and using mainly tick-boxes, to render the information clearer and also reduce the workload of the nurse/doctor as much as possible. After completion, the forms are forwarded to DHIR on a monthly basis where they are coded against the IDB Coding Manual Data Dictionary and then inputted in the main database at DHIR.

The Mater Dei Hospital (MDH) has been included in the system only recently. This required us to develop an electronic solution for data processing in the hospital, as the patient register in that hospital was already quite advanced and the use of stand-alone paper forms would have generated an excessive burden for the emergency department personnel. This hospital handles an average of ten thousand episodes per month.

A data mining software was developed to capture data from hospital records. The software makes use both of existing fields in the patient records, particularly the demographic variables, and also of a free-text field in which a short description of the episode is typically entered by the triage nurse.

This process helps not only in filtering injury episodes but also in pre-populating a number of variables for each episode. The software is capable of identifying acronyms/ terms/phrases/words to extract injury episodes. Relevant variables taken for each episode include anatomical site, injury type and objects involved.

Data collection at MDH started in January 2012 and DHIR staff are currently visiting the A&E personnel for short training and reach out sessions. Data is kept in accordance with the Data Protection Act, 2001. This allows an effective cross-link with hospital discharge registers and national mortality register in order to avoid duplications, to verify length of stay and death-related injuries and detect injuries bypassing emergency departments. A very high proportion of incidents lack data regarding place of occurrence, activity and objects involved.

Data use

The Injury Database is being consulted for numerous ad-hoc specific requests in response to policy or product safety queries. Information generated from the Database is disseminated both via regular reports and publications, and through communications in a variety of fora.

For more information:

audrey.galea@gov.mt

Country update on Injury Surveillance: the Netherlands

Introduction

In 1986, the Consumer Safety Institute in The Netherlands developed a system for the registration of injuries that are treated at Emergency Departments in Dutch hospitals. Main purpose was to gain insight on the number of injuries due to different types of accidents in the Netherlands, and to monitor the development of injuries through the years. A sample of ED’s started registering ED-treatments on Home and Leisure accidents. In 1997 the registration was extended to traffic accidents, accidents at work and injuries due to violence.

National IDB-system

Funded by the Ministry of Health, this Dutch Injury Surveillance System (DISS) currently operates in 14 ED’s and registers 80.000 – 100.000 injuries each year, representing an estimated 750.000 ED-treatments for injuries in the Netherlands. Participating hospitals directly deliver their injury data to the Consumer Safety Institute, where they are checked and processed. The collected data are analysed and reported by the CSI research department.

Use of data

These injury data from the Netherlands have guided preventive action throughout this 30-year period. Besides an important estimation of accidents in several injury fields, DISS has directed policy towards different injury risks for specific groups (e.g. falls in the elderly, child drownings), trends (e.g. an increase in sports injuries, alcohol intoxications) and new developments like skateboarding or electric bicycles. Medical costs and cost from absenteeism from work resulting from injuries can additionally be calculated with ED-data from DISS.

Data are used by many stakholders. Several ministries develop most of their policy towards prevention of injuries on information from the Injury Surveillance System. The ministry of Health based prevention of sports injuries on data from DISS for many years. The ministry of Infrastructure and Environment uses injury data collected around New Year’s Eve to monitor fireworks-related injuries. The Consumer Safety Institute itself based numerous preventive interventions on the information from DISS, for example prevention of child falls, drownings, intoxications and injuries through falls in the elderly. In addition, media welcome data on Emergency Department treatments to put news articles in perspective, like ED information on traffic accidents, drugs-related incidents, sports injuries, and the like.

Future outlook

In recent years, new developments have been started, in order to improve the quality of the collected information and minimize the actual work load in the hospitals themselves. Currently, DISS hospitals are gradually adapting their registration to a new system, where hospitals only deliver data that are already registered in their own hospital system, accompanied by an extensive injury narrative. Through text analysis, this narrative delivers all further information, which is automatically coded into the relevant variables. With this new approach,  collection, checking and processing of injury data is standardized (no bias resulting from different coders) and will take less time and effort, both for hospital staff as for the Consumer Safety Institute, in the future. A further increase in the number of hospitals in the Injury Surveillance System is in progress.

More information:

h.valkenberg@veiligheid.nl

IDB-related publications:

Kerncijfers LIS (Key figures DISS)

https://www.veiligheid.nl/organisatie/actueel/nieuws/ruim-2-miljoen-seh-bezoeken-in-2015

Vuurwerkongevallen type vuurwerk en letsel 2015-2016 (Fireworks-related injuries)

https://www.veiligheid.nl/organisatie/actueel/nieuws/opnieuw-fors-minder-vuurwerkslachtoffers

Alcoholvergiftigingen en ongevallen met alcohol (Alcohol-related incidents).

https://www.veiligheid.nl/organisatie/actueel/nieuws/alcoholvergiftiging-op-de-seh-in-2015-weer-gestegen

65 jaar en ouder (Falls in older people).

https://www.veiligheid.nl/valpreventie/kennis-en-cijfers/cijfers

Monitor drugsincidenten (Drugs-related incidents).

https://assets.trimbos.nl/docs/eb36c36b-f945-49f6-ad06-4cd56659a4f0.pdf

Emergency department visits due to vertebral fractures in the Netherlands, 1986-2008.

https://www.ncbi.nlm.nih.gov/pubmed/22055140

The economic burden of injury: Health care and productivity costs of injuries in the Netherlands. https://www.ncbi.nlm.nih.gov/pubmed/27177394

Incidence and costs of bicycle-related traumatic brain injuries in the Netherlands.

https://www.ncbi.nlm.nih.gov/pubmed/25939135

Country update on Injury Surveillance: Norway

Background

In Norway, counting a population of about 5 million inhabitants, each year 1800 persons die and about 500.000 persons are treated by a medical doctor due to an accidental injury. These figures gave enough reasons for the Norwegian government to issue a national strategic plan for prevention of accidental injuries for the period 2009-2014, which was co-signed by eleven ministers. This strategic plan is covering the whole field of accidental injuries: traffic, occupational, poisonings, burns, injuries in kindergarten, schools, sports, and injuries related to consumer products.

This plan is the latest in a series of plans developed over the past 20 years. It started in the nineties with a governmental action plan on home and leisure accidents with four ministers signing. In the following years more and more ministers were involved in such plans. This latest plan, issued in 2009, is covering first time ever the entire field of accident prevention.

One of the main targets in this is to get an overview of magnitude and severity of medical treated accidental injuries in Norway. This is needed for enabling target setting for various categories of injuries covered by the respective ministries. A sound injury registration system for medically treated injuries is indispensable for setting such targets. Because this is still not achieved, the plan is now prolonged until 2018

Methods

Over the years 1985-2002 a national injury registration system (in- and outpatients) was in place involving hospitals in four towns across Norway. However, it was discontinued in 2003 due to financial constraints as the comprehensive data set recorded (NOMESCO) required extra resources for registration and analyses (about 7 Euro per injury).

A new system emerged in 2005. The design included a minimum data set (MDS) integrated in the patient-administrative system to be registered in the routine in all hospitals (N=60) at no extra cost. Such a task should require at maximum one minute and should be easy enough to be done by a receptionist. Through collaboration with other authorities, especially in the fields of traffic and occupational safety, a MDS was developed. The parliament decided in 2009 to have such a system becoming mandatory for all hospitals. A unique birth number is allowed to be included without permission form the patient. The data are sent to the National Patient Register (NPR) for analyses and dissemination. An report is made for each year since 2011.

The Minimum Data Set consists of following data elements:

- From the “regular” patient journal to be extracted: Personal data as sex, age, municipality of living, injury diagnoses (ICD 10).

- Additional MDS-elements to be collected from patient: Date and hour for injury; Type of intent: accident, violence, self-inflicted; Municipality injured; Place of occurrence, if street: traffic accident Yes/no, if yes: means of transport; Activity when injury occurred, if occ. acc.: type of industry; Injury mechanism; and Injury severity (AIS).

Preliminary results

About 300.000 patients are treated annually for an injury in the 60 hospitals as in- and out patients. In addition, about 250.000 patients are treated in the primary health system, consisting of about 4.500 general practitioners and 330 municipality AEDs across Norway.

A few of the hospitals have high completeness in registration of the MDS, but most not. Average completeness for all 60 hospitals is now 42 %. Reasons for low completeness are that most injury data elements are of non-medical nature, therefore seldom of great interest for the hospitals; IT-software is often hampering seamless registration during treatment; Insufficient capacity in NPR to give feedback to the hospitals and respective communities.

Use of data

We analysed the more severe injury diagnoses for 2010-14 for population in Vestfold, a county with14 municipalities among which nine are a Safe Community. The result of the analyses is promising in order to give the municipalities monitoring injury data to help them in their prioritizations.

There are some excellent examples of the use of injury data for prevention actions in local communities. A medical officer in a small municipality, Os i Østerdalen, has reduced fall and agricultural injuries by collaborating with local authorities and voluntary organisations based on injury registration of all injuries in the municipality. Hip fractures for instance were reduced by 50 % in Os in the winter by gravelling icy staircases and paths around their houses.

The same has happened in Harstad, a small city in the North of Norway, where fall injuries in the  homes for 65+ were reduced by 26 % in the winter by 49% and burns in children treated as in-patients were reduced by almost 100 % over a couple of years-time. These two examples illustrate the potentiality for injury prevention based on injury registration.

More information:

Johan Lund

johan.lund@medisin.uio.no

IDB-related publications:

https://helsedirektoratet.no/publikasjoner/personskadedata

This link goes to the annual reports 2010-15 from the National patient register.

https://helsedirektoratet.no/nyheter/flere-syklister-gir-tryggere-syklister

A one year in-depth study of bicycle injuries treated at the Oslo AED, a part of our national injury register, treating ab. 50 000 injuries a year.

https://helsedirektoratet.no/nyheter/mange-smaskader-i-skole-og-barnehage

A one-year in-depth study of injuries in kindergarten and schools, at the Oslo AED.

https://www.fhi.no/publ/2014/skadebildet-i-norge-hovedvekt-pa-pe2/

Report on the Injury Pattern in Norway, made by the Institute of public Health.

Country update on Injury Surveillance: Portugal

Introduction

In Portugal, the National Health Service (NHS) is responsible for providing health care to its ten and a half million population.  A growing private and social sector also provides health services. In the Portuguese health care system there are three overlapping systems: the NHS; special public and private insurance schemes for certain professions (health subsystems); and private voluntary health insurance.

Health service planning and regulation largely take place at the central level in the Ministry of Health (MoH) and its institutions, through its National Health Plan. The management of the NHS is devolved to the

5 health regions: Norte; Centro; Lisboa e Vale do Tejo; Alentejo; and Algarve. In the 2 autonomous regions, Azores and Madeira, regional secretaries of the regional government are responsible for health care and planning and evaluation of health. In these autonomous regions health policy followed the general constitutional principles of the NHS, however it is applied locally by the regional governments who have some flexibility.

Primary care centers are the central pillar in the health system carrying an important role in health promotion, prevention and care of the disease, continuity of care and collaboration  with other health services. The administrative boards of each of the 5 mainland health regions are accountable to the MoH and are responsible for strategic management of population health, supervision and control of hospitals, management of primary care/NHS primary care centers, and implementation of national health policies taking into account regional needs.  The NHS operates the 65 hospitals that have an Emergency Department (ED).

Injury awareness among public health care providers has been reinforced by the adoption of the National Programme of Prevention of Injuries 2009-2016, now under review for extension until  2020. This programme aims to reduce the frequency of injuries and their impact on the general population and specially on vulnerable groups as well as to ensure equitable access of injured persons to health care. It also highlights the need to collect, analyse and disseminate information on unintentional injuries through an integrated system of information.

Results from the last Census in 2011 indicate that 15% of the population in Portugal belongs to the age group 0- 14 years and about 19% is 65 years or over, while in 2001 these proportions were 16% and 16,5% respectively. This trend is expected to continue and certainly will have an impact on the annual number of injuries.

National IDB-system

Since 1986, Portugal participates in EC projects for collecting injury related  data from Emergency Departments in a sample of public hospitals. These studies were coordinated by the national Consumer Safety Department. After the end of the EC-sponsored consumer injury data collection programme in the late 90’s, the Ministry of Health took over the coordination of the injury surveillance system EVITA in 2002. EVITA is now managed by the Portugal National Institute of Health Doutor Ricardo Jorge – INSA and is based on routine data collection on home and leisure accidents (HLA) in a sample of emergency health units of the NHS.

The main objectives of the system EVITA are to detect:

- Short-term trends: identify the frequency of HLA in general and the various types of injuries, as well as the characteristics of victims and the circumstances of injury events;

- Long-term trends: identify risk-prone situations, establishing a support base for developing and refining consumer protection regulations and enforcement based on evidence. Disseminate information and stimulate research.

Module EVITA consists of a dialog box, and collects information on the accident event and its circumstances, as well as characteristics of the injury. The following fields are available in this module:

- Sex and Date of birth of the victim;

- Date and time of care in the emergency room;

- Date and time of injury;

- Location and activity of the injury and

- Mechanism & Part of body injured.

The recording of data is supported by a modular software application, Module EVITA, which runs within the SINUS- and SONHO-programs of MoH. Data capture is done by the health service receptionist at the time of registration of the patient, in accordance with instructions provided by INSA.

Insights gained

Data from the Hospital Discharge System show that from 2013 to 2015, 16.4 % of all hospital admissions were injury cases that correspond within the type of injury reported in the system EVITA. The average stay in hospital was 5.8 days.

During the same period, EVITA collected data on 26.713 injury cases (the number of ED and health centres participating varied). As for sex distribution in the years 2013-2015 data shows that in all group ages until 54 years men are more affected by injuries than women, but after 54 years the proportion of women exceeds that of males, which may also be reflecting the demographic structure.

Future outlook

Changes in NHS hospital management structures in 2009 and the reorganization of primary care system has led to a slowdown of notifications by the EDs. Due to these  developments the sample had to be rebuilt. Also, now the JAMIE-methodology has been agreed at EU-level, some changes are required in the instructions and the codification scheme of the data, which changes are expected to be fully implemented in the year 2017. A new training programme and supporting materials are being developed at INSA to strengthen the link with the health institutions participating in the EVITA network. Work with the national health informatics service is ongoing to expand the sample registering injury cases with EVITA.

Strategic health advisors, decision makers, consumer  organizations, public health professionals, the media and university researchers are the main users of the data.

More information:

mariana.neto@insa.min-saude.pt

IDB-related publications:

Barros P, Almeida Simões J. Portugal: Health system review. Health Systems in Transition, 2007; 9(5)

https://www.ncbi.nlm.nih.gov/pubmed/22222781

INE (2016). Estatísticas da Saúde 2014 (Health-related statistics, 2014). Lisbon, National Statistics Institute

https://www.ine.pt/xportal/xmain?xpid=INE&xpgid=ine_publicacoes&PUBLICACOESpub_boui=257402707&PUBLICACOEStema=55538&PUBLICACOESmodo=2

Country update on Injury Surveillance: Romania

Introduction

In Romania injuries are the fourth leading cause of death for all age groups and the leading cause of death in children and adolescents aged 0-19 years. As stated in the hospital discharge statistics, at national level around 30.000 people received advanced care due to an injury in 2010. The death rate for all types of injuries is 57.2/100 000 inhabitants in Romania, while the EU average rate is of 40.0/100 000.

Romania still lacks a well-established national injury monitoring and surveillance system, therefore, we expect that the real burden of injuries is underestimated. Moreover, there is no national policy ensuring that injury prevention strategies are adopted and implemented. Considering the high costs of injury treatment and care, continuous collection of data on injuries at national level is desperately needed.

Implementing the work of EU-IDB in Romania was the first initiative to have injury surveillance, first as a pilot in one emergency department, followed by other four emergency departments as part of the JAMIE Project. Unfortunately, the system was not adopted by the Ministry of Health as part of the core emergency data surveillance. Romania still lacks of a sustainable injury surveillance system.

Insights gained

Since 2012, the Department of Public Health tries to extend the pilot initiative and to include more hospitals and all ages. Through analysis of these data assault, self-harm, and falls were added to this list of injuries with high incidence.

The health systems in the region are in transition, with growing attention to improving health infrastructure. However, acute care systems are lagging behind international standards, one of them being lack of injury surveillance systems. Therefore, there is still an urgent need of a sustainable data collection system on injuries in the Romanian emergency department.

Use of data

The data is being used by the Department of Public Health, College of Political, Administrative and Communication Sciences for research and dissemination purposes. Data collected as part of the EU-IDB project was used in several peer-reviewed publications, to develop policy briefs for evidence informed policymaking, and to support other independent research in the field. Data was disseminated to both local and national authorities to support a national injury surveillance system in Romania.

Child safety is another emerging issue on which the Department has concentrated efforts by conducting research and health promotion activities in the field. Using IDB as baseline data we have developed a study to document the use of child restraint systems: Child Safety Survey in Cluj-Napoca, funded by the University of Iowa, Injury Prevention Research Center. The study had a great visibility in the community.

The Department used data to document and support the Save Kids Lives Campaign in Romania (2015) is partnership with the Cluj County Police Inspectorate. A child passengers’ safety raising awareness week to inform parents on how to properly use child safety restraints was organized. Parents received leaflets with a checklist to guide them on how to choose child seats and booster seats appropriate for their children’s height and weight and encourage them to look for more information.

More information:

diana.rus@publichealth.ro

IDB-related publications:

Epidemiology of road traffic injuries treated in a large Romanian Emergency Department in Tîrgu-Mureş between 2009-2010. Traffic Inj Prev, 16(8):835-41. Link to the abstract.

Paediatric head injuries treated in children’s emergency department from Cluj-Napoca, Romania. International Journal of Injury Control and Safety Promotion. 23(2): 206-213. Link to the article.

Epidemiology of assault and self-harm injuries treated in a large Romanian Emergency Department. Eur J Emerg Med. 19(3):146-52. doi:10.1097/MEJ.0b013e32834ada2e. Link to the article.

IDB – The link between Emergency Department and Injury Prevention. Jurnalul de Medicină de Urgenţă şi Salvări în Situaţii Speciale, No: I./2011/Anul III. ISFN: 2066-0278

Policy briefs available on the institutional website of the NDA in Romania, resources section:

- Reducing children’s unintentional injuries. The English version of the Policy Brief no. 1 can be downloaded here.

- Minimum data collection MDS-IDB. The Romanian version of the Policy Brief no. 2 can be downloaded here.

- Potentially dangerous products for children.  The English version of the Policy Brief no. 3 can be downloaded here.

Country update on Injury Surveillance: Sweden

Background

In Sweden, around 5 000 persons die every year as a result of an injury event; about 150 000 persons are discharged from hospitals for the same reason and approximately 500 000 individuals are treated as outpatients at hospitals. An unknown number of persons are treated in health care centres or by a general practitioner.

As in most other European countries, in Sweden the number one killer among children and young adults is injuries. In the same age-group, injuries are also the most common reasons for hospital admissions. It is therefore very important to continue to invest in injury prevention and safety promotion.

However, to be successful in injury prevention, it is essential to know how, when, where and why injuries occur. Sweden has nationwide population-based registers on fatalities, hospital discharges and Emergency Department-attendances. These registers are all based on ICD-10, which works quite well for monitoring injuries and their treatment, but not for prevention purposes as they lack detailed information about the causes and circumstances of injury-events.

How it started

Sweden became a member of the European Community in 1995, and during that very same year, Sweden adopted the so-called EHLASS system, a European injury data exchange program that focused on home and leisure accidents. However, quality controls revealed quite soon that collecting only home and leisure accidents resulted into deficiencies in data capture and into a high percentage of missing cases. To manage that problem, it was decided to expand the scope of the system and to collect information on all injuries – both unintentional and intentional- and in line with the successor programme of EHLASS: the European Injury Data Base (IDB).

In 1999 an “all-injury” data collection was started and at the same time IDB-Sweden became a formal part of the nationwide National Patient Register. This implies that the personal Identification number could be added to the Information about the injury event. Now IDB-Sweden can be linked to other registers, like the population register or the hospital discharge register.

Over the past few years, IDB-Sweden included a varying number of hospitals, between three and nine. Together these hospitals cover five to nine per cent of the entire population.

Current situation

IDB Sweden is managed by Socialstyrelsen, the National Board of Health and Welfare (NBHW). The NBHW is the national office for collecting statistics in the health and social welfare sector. IDB-Sweden is built on the basis that the County Councils, who actually run the hospitals in the counties, are the owner of their injury data.

The NBHW is a data-user who buys this information. When the data reach the NBHW, their quality is checked and the data are compiled into a national database. The staff of IDB Sweden consists of one full time employed data administrator who analyse and report on the injury statistics.

At present, six hospitals, based in three different counties, are reporting to IDB Sweden. The coverage is now about seven per cent of the population. The data are collected at emergency departments, where the circumstances of the injury event are reported either by the injured person or by an accompanying person. The administrative data and the diagnosis are completed by the medical staff. The collected information is classified and coded by trained staffers before it is submitted once a year to the National Board of Health and Welfare where the data are checked and uploaded into the national database IDB-Sweden.

Altogether, information on approximately 46,000 injury events will be reported in the 2015 database.

The vision is that IDB Sweden, together with injury data from the nationwide registers on cause of deaths and in- and outpatient treatment at hospitals, will function as a representative national information system on injuries. To fulfil the vision, the number of hospitals reporting IDB-data must be increased.

Data use

The statistics from IDB Sweden are used by a wide range of authorities, organisations, mass-media and educational institutions. The government also use  IDB-statistics – one example is “the investigation about children’s safety at preschool".

For some national authorities, for example the Swedish Consumer Agency and the Swedish

Contingencies Agency IDB Sweden is a most valuable information tool for their injury prevention work. As the participating hospitals own their data, they are also encouraged to use them for local injury prevention actions. Statistics from IDB-Sweden are also used for raising public awareness and for media campaigns.

In conclusion

As IDB contains unique and detailed data on injury events, it is very important to ensure that the data remain accurate and help to produce national representative data. The financing of the existing system must be secured, as well as a further extension of the number IDB-reporting hospitals to guarantee the representativeness of the data.

More information:

Pernilla.Fagerstrom@socialstyrelsen.se

IDB-related publications:

Skador bland barn i Sverige – Olycksfall, övergrepp och avsiktligt självdestruktiva handlingar http://www.socialstyrelsen.se/Lists/Artikelkatalog/Attachments/19701/2015-2-8.pdf

MSB – Swedish Civil Contingencies Agency has published a lot based on IDB. For instance on this webpage fact sheets about  specific accidents among children https://ida.msb.se/ida2#page=a0039 (Only available in swedish).

Thodelius, Charlotta, Risker och rum. Riskmiljöer och riskfaktorer för barn och ungas skadehändelser i hem- och boendemiljön., Chalmers University of Technology, 2016

http://publications.lib.chalmers.se/records/fulltext/241900/241900.pdf  (Only the abstract is in english)

Better Safety on Quad Bikes : Joint strategy version 1.0 for the years 2014-2020. Rapport 2013:153. Borlänge: The Swedish Transport Administration, Trafikverket.

http://www.trafikverket.se/contentassets/2155fdbb83f445adb2c2789407134370/strategi_fyrhjuling_eng.pdf

Nilson, Finn, Fall-related injuries amongst elderly in Sweden [Elektronisk resurs] : still an emerging risk?, Fakulteten för hälsa, natur- och teknikvetenskap, risk- och miljöstudier, Karlstads universitet, Diss. (sammanfattning) Karlstad : Karlstads universitet, 2014,Karlstad, 2014

http://urn.kb.se/resolve?urn=urn:nbn:se:kau:diva-31727

Svee, A, A Jonsson, F Sjöberg, and F Huss. “Burns in Sweden : Temporal Trends from 1987 to 2010.” Pending Publication (Annals of Burns and Fire Disasters, n.d.) http://www.medbc.com/meditline/articles/vol_40/num_2/text/vol40n2p1053.pdf.

Pohl, Petra, Falls in older community-dwelling women and men risk factors and safety strategies. Fall risk awareness, fear of falling, and preferred exercise properties from a gender perspective., Umeå Universitet, Umeå, 2015 (Only Umeå data)

http://umu.diva-portal.org/smash/get/diva2:782389/FULLTEXT01.pdf

Country update on Injury Surveillance: Slovenia

Background

In Slovenia injuries are one of the major public health problems that the government needs to address. When all age groups are taken together, injuries rank the third after cardio-vascular diseases and neoplasms and cause 1.400 deaths per year. Injuries are also the second leading cause of healthy life years lost because they disproportionately affect younger people and high burden in young people reflects both a greater number of years of life lost and more years lived with disability for the survivors.

The health sector plays an important role in multi-sectoral approach to injury prevention by developing injury surveillance system, research, setting priorities for action plans and developing interventions.

How it started

National mortality and hospital discharge statistics provide key information about external cause and type of injury which has been used for national policies and setting priorities for injury prevention in Slovenia.

But some information for guiding comprehensive policies and developing specific injury prevention interventions was still lacking, in particular information about activities, involved products, services and environments where accidents occur, the precise injury mechanisms and their consequences.

In order to obtain additional information on risk factors for injuries a new injury database was developed as a part of the National Hospital Information System and was implemented in 1997. Data collection was mandatory for all Slovenian hospitals according to national law on health information system and databases. The Injury dataset covered information on hospital, injured person, nature of injury, external cause, place, activity when injured and the 10th revision of ICD was introduced into health information system.

In 2004 Slovenia joined the EU Injury Database (IDB) project to participate in building a common European injury surveillance system. At that time it was not feasible to extend injury data collection to emergency departments according to IDB methodology due to national legislative restriction, so then decision was taken to supplement existing hospital admission dataset with new data elements and classifications and improve data reporting to European Injury Database. For the first time it was possible to present national data on injuries and poisonings by selected product, mechanism, detailed place of occurrence and detailed activity when injured.

Data from emergency departments

In 2011 Slovenia joined the JAMIE project and the problem with legislative restriction of data collection at emergency departments was solved by using new methodological approach based on national sample of hospitals, which provide enough information for prevention purposes and allow for national estimates of incidence rates.

In Slovenia emergency department data on injuries and poisonings are part of the Out-Patient Specialist Services Database, where reports are submitted for each patient treated in the out-patient specialist services. Due to the fact that the Out-Patient Specialist Services Database is normally submitted to National Institute of Public Health (NIPH) in aggregated form without personal identifier, it was necessary to introduce a separate data capture of individual level records for the purpose of FDS and MDS data preparation, based upon special agreements with four selected sample hospitals, which are representative for the entire country, from 2011 onwards. Captured data for years 2011 to 2014 were then transformed into standard FDS data format according to the Injury Database (IDB) Coding Manual, version 1.1, June 2005 and MDS data format according to JAMIE Manual, August 2012 and by applying bridge coding from ICD-10 according to these coding manuals. In 2013 Australian modification of ICD-10 (6th ed.) was implemented in Slovenia, so from 2013 onwards bridge coding from ICD-10-AM (6th) to ICD-10 was applied to injury data before they were transformed into standard FDS and MDS data format.

At the moment, major renovation of the Out-Patient Specialist Services Database is taking place, so all the out-patient data, including emergency department data on injuries and poisonings, will be reported to NIPH as individual level records from 2018 onwards, and this will enable easy access to injury data in all Slovenian hospitals and its transformation into standard FDS and MDS data format.

Results

Emergency departments in Slovenian hospitals are not legally obliged to collect injury specific variables like place of occurrence, mechanism of injury, activity when injured and underlying object/ substance producing injury. Nevertheless, the injury specific data collected in the sample hospitals for years 2011 to 2014 proved to be to a large extent complete, which also indicates a good validity of the resulting national estimates. The MDS sample covers about 40% of all national discharges and more than 50% of all ambulatory emergency department treatments and FDS sample covers about 30% and 40% respectively.

Data use

Data on injury patterns related to selected products, mechanisms and detailed places of occurrence are used for developing a multi-sectoral child safety action plan, setting priorities, specific actions and preventive measures.

The National Institute of Public in Slovenia is now able to support proposed preventive measures by presenting data on children drowning in private swimming pools, scalds by hot water source, burns by place of occurrence etc. In general the majority of injuries are occurring at home and in leisure environment and most of them involve one or more products.

Data also allows the Institute to systematically monitor injury patterns related to products and places of occurrence and take them into account when designing products, buildings or when defining standards. Ministry of Economic Development and Technology frequently uses data on injuries due to selected products to support adoption of new standards and regulations in order to ensure a high level of safety of products and services for the citizens of Slovenia.

More information:

Tina.Zupanic@nijz.si

Country update on Injury Surveillance in the Navarra Region: Spain

In spite of WHO-European Region Resolution of 2005 and the European Council Recommendation of 2007, urging member states to enhance Injury Surveillance Systems, injury data is still scarcely available in Spain.  In the last four years, an increasing number of countries have gathered data about injuries and contributed to the EU Injury Data Base, but Spain has not contributed with any data yet, therefore we don’t know the real situation of this problem in our society.

Fortunately, the Ministry of Health in Madrid accepted in 2009 the invitation to join the JAMIE project and invited the Navarra Public Health Service (Servicio Navarro de Salud Osasunbidea) to take on board a pilot programme for the routinely collection of injury data in hospitals within the region.

Reasons for choosing the Navarra region

There are a number of strengths which were identified in the process of assessing the suitability of the region of Navarra to take part in the project:

- The relative small size of the region which makes the pilot more manageable to implement the system;

- Capability and willingness of the Navarra Accident and Emergency Services to participate;

- Track record of Navarra Public Health Service in providing good quality health care services.

- Positive on-going collaboration among A&E departments in hospitals taking part in the project.

- Support from the Navarra Regional Government which recognises the relevance and need of having an information system in place to collect this type of data.

As declared in a press conference on 14th March 2013 by Navarra Health Department.

These were the main considerations for the Ministry of Health in Madrid to charge the Navarra Public Health Service with the tasks to pilot test the implementation of an Injury Surveillance System and to gather data in hospitals, to design and develop an efficient and sustainable methodology in order to provide data and to become a National Reference for future implementation in other regions and share best practice as a result of our experience.

Navarra Region

Navarra covers an area of 10.421 Km² and counts almost 637.000 inhabitants. There are three hospitals that provide accident and emergency services, i.e. in the following cities: Pamplona, Estella and Tudela. The three public hospitals share one and the same patient recording software. About 80% of A&E patients are codified according to   ICD-9. The original information system in place was designed for clinical rather than epidemiological purposes and therefore, some changes need to be incorporated in order to provide data as requested.

Data collection efforts in 2013

The main work this year consisted of collecting data according to the Minimum Data Set in 2013 on the expected 30.000 cases that will be treated in the three hospitals over a twelve months period. In addition, in one hospital data will be collected in compliance with the Full Data Set requirements. These data will be collected by reviewing ‘clinical health records’ retrospectively during 2013.

Existing data will be converted into variables as required by JAMIE. The completed sets will be then analysed in collaboration with the Barcelona Public Health Agency.

In collaboration with Ministry of Health the results obtained will be evaluated and possible ways for improving Spain´s representativeness of data for the entire nation will be explored. The accumulated experience since we joined JAMIE and the need to adapt our data to European requirements let us envisage the possibility of speeding up extraordinarily this arduous task by automating the data collection/process whenever it is possible and by developing a specific tool. An information system will be developed which will allow the automatic conversion of data from existing clinical health records entered by physicians in A&E services

Preliminary results first two months

The preliminary results of two-month collecting data (pediatric patients excluded) are presented according to age and numbers:

| Causes | Frequency | Ratio | Valid ratio |
| --- | --- | --- | --- |
| Traffic accidents | 268 | 10,5 | 10,6 |
| Fall | 1.067 | 41,7 | 42,4 |
| Injury | 302 | 11,8 | 12 |
| Poisoning | 50 | 2 | 2 |
| Burn | 28 | 1,1 | 1,1 |
| Others | 803 | 31,4 | 31,9 |
| Sub-total | 2.518 | 98,5 | 100 |
| Missing | 39 | 1,5 |  |
| Grand-total | 2.557 | 100 |  |

The data collected provide indications as to specific population groups and risk areas that deserve increased attention in the framework of our policies for health and consumer protection. These include home accidents, in particular accidental poisonings and burns and scalds in children and older people, falls among older people and domestic violence (child abuse, elder abuse).

The knowledge of these circumstances will enable us to develop policies and procedures and implement public health measures (as it was previously done in the field of traffic accidents) which will enable us to reduce morbidity and mortality due to these causes and improve health and quality of life in the region.

More information

Tomás Belzunegui Otano, tbelzuno@navarra.es, Principal Investigator. Hospital Complex of Navarre  Marisol Fragoso Roanes, mfragosr@navarra.es, Project Manager. R&D Project, Management Unit. Navarrabiomed – Miguel Servet Foundation www.navarrabiomed.es

Country update on Injury Surveillance: Turkey

Introduction

Turkey is a democratic, secular, constitutional republic with a diverse cultural heritage. According to the Address-Based Population Recording System of Turkey, the country's population was 78.7 million people in 2015.

Since its establishment in 2012, the Public Health Institution of Turkey (PHIT) is the main agency carrying out of the primary and public health services including preparation, implementation, coordination and assessment of programmes, plans and activities across the country in order to enhance public health in accordance with the national targets.

In addition to the public health commitment to injury prevention, the consumer policy perspective also provides a relevant angle for government-driven interventions for protection of health and safety of citizens. Market surveillance and inspection is an important tool for the competent the market authorities in protection of consumers against nonconforming or inherently dangerous consumer products. In Turkey, various ministries, agencies and institutions are involved in market surveillance activities and are coordinated by the Ministry of Economy.

A National Market Surveillance Strategy Document (2010-2012) was published by the Ministry of Economy. This strategy document includes the firm commitment of the Government to establish an injury database, enabling to record injuries and accidents related to consumer products and to share them with the competent authorities responsible for market surveillance and inspection.

National IDB-system

The PHIT has undertaken the operation of the injury data base and has initiated the work on enhanced injury monitoring in emergency departments at hospitals in cooperation with the Public Hospitals Agency of Turkey.

All relevant ministries, agencies, institutions responsible for ensuring the product safety as well as  academic institutions and NGOs have been informed about the development of National Accident and Injury Database.

National Accident and Injury Database is a web-based platform. In addition to the full dataset of European Injury Database, some extra variables are included, i.e. level of education of injured people, characteristics of products and possible product failures. The Coding Manual has also been updated in accordance with the requirements laid down by the institutions responsible for product safety in the country.

The data can be accessed online with the user name and password by the authorized data entry staff. This enables the PHIT to follow up and assess the number of data entered by the staff and their individual performances with regard to data quality.

Main quality control points have been integrated into the database. It is designed to warn user when inconsistent data in data record or blanks in obligatory fields are being detected. Data entered into the system via web application are stored in a data warehouse of the Ministry of Health (MoH), ready for instant inquiry. Assessments made with business intelligence applications are shared with decision makers.

Insights gained

In the years of 2012-2014, cases were randomly selected in the emergency departments of 15 hospitals representing the country and data were collected. In 2015 and 2016, data entry was enlarged to 16 hospitals. According to the analyses, monitoring of the data by hospital managers was found to have a positive effect on data entry and reporting modules were prepared to enable monitoring of by the manager of each hospital.

By the end of 2015, 40,381 data were recorded in the National Accident and Injury database. In October 2016, 42,654 data were recorded. The work has been initiated to improve the standards of data collection and to enable sustainability of work to be finalized by the end of 2017.

To ensure the efficiency, priority is given to improve cooperation in prevention among the institutions and to increase the awareness among citizens thereby reduce the number of injuries in the society. Since 2015, regular meetings with stakeholder organizations has been initiated in order to prepare and implement accident and injury prevention programs.

For further information:

banu.ekinci@saglik.gov.tr

Related links:

http://kronikhastaliklar.thsk.saglik.gov.tr/daire-faaliyetleri/ukay.html

http://kronikhastaliklar.thsk.saglik.gov.tr/daire-faaliyetleri/ukay/1125-ulusal-kaza-ve-yaralanma-bilgi-notu.html

http://kronikhastaliklar.thsk.saglik.gov.tr/Dosya/Dokumanlar/ukay/EuropeSafe_Master_R4_SinglePage_12102016.pdf

http://kronikhastaliklar.thsk.saglik.gov.tr/Dosya/Dokumanlar/ukay/ukay_2012_2014.pdf

Country update on Injury Surveillance: United Kingdom

Introduction

The UK has a long history in injury surveillance, having developed the Home Accident

Surveillance System (HASS) and Leisure Accident Surveillance System (LASS) which contributed to development of the European Home and Leisure Accident Surveillance System (EHLASS), the precursor to the Injury Data Base (IDB).  Unfortunately the HASS/LASS systems ceased operation in 2002; however, several other Emergency Department (ED) based surveillance systems have been in operation across parts of the UK over the past 15 years, including the All Wales Injury Surveillance System (AWISS)1.

The UK has been involved in the IDB project since initial discussions as part of the JAMIE project.  It is important to note that health is a devolved issue in the UK and hence each of the UK countries (England, Scotland, Wales and Northern Ireland) develops its own health policy.  In general, there has been support from health ministries for the IDB concept.  However, given current financial pressures it has been difficult to find funding for injury data collection across the UK.

National IDB-system

The UK responded to the IDB challenge by first exploring to what extent current data collections systems met the needs of the IDB Minimum and Full Data Set (MDS and FDS).  Unfortunately, no hospital in the UK has collected data at the FDS level since the demise of the HASS and LASS system in 2002, and it has not been possible to fund the development of a new system since.  However, select existing ED systems have been deemed suitable to contribute data towards the less detailed IDB-MDS.

Initially, UK MDS samples were based on ED data from a sample of hospitals in England.  However, upon further investigation the quality and completeness of data coding in these hospitals was deemed unsatisfactory. Further, it was not possible to establish fall related ED attendances in English ED data, a leading mechanism of injury in the UK.   Therefore, we explored the potential to use ED data collected in Welsh hospitals as part of the AWISS (an injury surveillance system based on injury related attendances to Welsh ED departments).

Once again considerable variation was observed in coding quality and completeness between Welsh hospitals; however, 5 hospitals were of sufficient quality, with over 75% completeness in all relevant diagnosis and aetiology fields.  These 5 hospitals comprised of 2 major EDs located in the North and South of Wales, and 3 minor injury units based in South Wales.  It should be noted that in 4/5 hospitals only three character ICD-10 codes were recorded in the diagnosis fields.  As the 4th character is required to accurately map injury diagnoses to the MDS, proportions of injuries observed in national ED attendances in Denmark were used to map 3 character ICD10 codes to 4 character codes and use this distribution to impute the missing data.  AWISS is hosted by the Farr Institute and Prudent Healthcare Intelligence Hub at Swansea University in Wales, which also coordinates the UK’s IDB-MDS submissions.

Insights gained

Table 1 presents an overview of the UK’s IDB-MDS samples and crude incidence rates. As AWISS collects data on all injury related ED attendances in Wales, national ED attendances were used in the calculation of the UK’s reference populations. The IDB has revealed that the UK reports some of the highest injury related ED attendance rates across Europe.   The leading cause of injuries attending EDs in the UK are falls (39%) followed by other causes (29%), cuts and piercings (5%), road traffic collisions (5%), poisonings (1%) and burns (1%).  20% of injuries were recorded in our sample as being of ‘unknown’ cause. The IDB has helped exposed emerging trends in the UK such as the increase in self-harm related attendances in females aged 15-24, with rates increasing from 690 per 100,000 population in 2010, to 878 per 100,000 in 2015.

Table 1 - UK IDB-MDS data overview by year

| Year | Injury related ED attendances in UK IDB-MDS sample | No. of hospitals included in UK IDB-MDS sample | Reference population | Crude incidence rate (per 100,000 population) |
| --- | --- | --- | --- | --- |
| 2010 | 51930 | 4 | 604508 | 8590 |
| 2011 | 83558 | 5 | 789058 | 10590 |
| 2012 | 89600 | 5 | 843247 | 10626 |
| 2013 | 84202 | 5 | 763793 | 11024 |
| 2014 | 81450 | 5 | 722167 | 11279 |
| 2015 | 81817 | 5 | 718405 | 11389 |

Use of data

Several injury prevention related organisations have utilised the IDB database in the UK including: The Royal Society for the Prevention of Accidents (RoSPA), Children in Wales, universities, and UK governments and health organisations.  Data requests have ranged from queries about trampoline injuries in children to comparative country-level analyses of the incidence of traumatic brain injuries.

Future outlook

Several avenues are being explored to improve the UK’s IDB submissions as well as the overall value of the injury data, including:

- implementing an extended version of the MDS dataset directly into ED data collection systems in the UK in line with the College of Emergency Medicine’s new data set;

- the potential to use automated natural language processing software to convert narrative information collected on presenting complaint and diagnosis fields in ED systems into the FDS coding; and

- leading the development of an online IDB based burden of injury calculation tool.  This tool will enable countries to compare injury related Disability Adjusted Life Years (DALYs) by country, year, gender, age, and key injury domains.

More information:

s.turner@swansea.ac.uk

IDB-related publications:

1. Lyons, Ronan A., et al. "226 Using Long bone fractures as an injury incidence indicator in Europe." Injury Prevention 22.Suppl 2 (2016): A82-A83.

2. Turner, Samantha L., et al. "The European injury data base: supporting injury research and policy across Europe." Injury Prevention 22. Suppl 2 (2016): A80-A81

3. Lyons, Ronan A, et al. "Joint action on monitoring injuries in Europe (JAMIE): development of a new minimum data set (MDS)." Injury Prevention 18.Suppl 1 (2012): A234-A234.

4. EuroSafe: Injuries in the European Union, Summary on injury statistics 2012-2014, Amsterdam 2016

Annex 4: List of proposed improvements of EU IDB web-gate

PUBLIC ACCESS APP

0.	All references to DG SANCO should be changed to DG SANTE.

- 1. The page title of the public access result page shall be corrected from 'Welcome in IDB Public' to 'Welcome to the IDB Public Access”

- The column titles (result page) shall be expanded or corrected:

- 'Nb Cases' shall be replaced by 'IDB Sample Cases'

- 'Incidence Rate per 100.000 inhabitants' needs to be corrected to ‘Estimated Incidence Rate per 1000 Inhabitants’

- ‘Country Cases’ shall be replaced by ‘Estimated National Cases’

- Additional information is desired when users hover over these titles of the result table:

- ‘IDB Sample Cases’: Additional info = ‘No. of injury cases submitted to the IDB on the given year’

- ‘Estimated National Cases’: Additional info = ‘Estimated number of national cases, based on the estimated rate and population on 1 January on the given year’

- Estimated incidence rate shall be always displayed to 1 decimal place

- In accordance with confidentiality requests, no counts less than 5 should be displayed. If a count is below 5, please display always ‘<5’

- Sometimes where the reference population isn’t available the incidence rate and country estimates read zero. These cells shall be better left blank instead.

- Please update the incidence rate label on the bar chart to ‘Estimated Incidence Rate per 1000 Inhabitants’

- A key needs to be added to the map as it is unclear what the different colours of the countries represent (for sample cases, national cases as well as national incidence rates).

- It would be helpful to display the actual national estimates (sample cases, national cases, national incidence rates) when hovering over the countries.

- “Filters by countries”: Please add “all countries” and “EU28” as selection option. The estimate for “all countries” and “EU countries” shall be calculated as simple average of available rates, with the number of countries, where rates are available, as denominator.

- Please correct “selection criteria” to “selection criteria”.

- In the list of “selection criteria” please change the last line from “Echi29” to “European Core Health Indicators (ECHI)”

- Please add to the selection criterion “European Core Health Indicators (ECHI) the following:

- ECHI-29b: Home, leisure & school accidents: Intent = 1 (accident) & Mechanism = 2 - 8 & Activity = 2 or 8

- Road traffic accidents: Intent = 1 (accident) & Mechanism = 1 (road traffic injury)

- Work place accidents: Intent = 1 (accident) & Activity = 1 (paid work)

- School accidents: Intent = 1 (accident) & Location = 2 (educational establishment)

- Sport accidents: Intent = 1 (accident) & Activity = 2 (sports)

- Interpersonal violence: Intent = 3 (assault)

- Deliberate self-harm: Intent = 2 (deliberate self-harm)

- Would it be possible to display the actual definitions of the indicators e.g. in additional information boxes appearing when hovering over indicator titles?

15. On this page, would it be possible to have a logo of the current version of IDB?

RESTRICTED ACCESS APP

- Correct the misleading link at page https://webgate.ec.europa.eu/idb/ “request an access to IDB”, which suggests a direct procedure for getting access to IDB FDS microdata. Instead to the EU Login this button should lead to page http://ec.europa.eu/health/data_collection/databases/idb/restricted_access_en, where instruction is provided how access to IDB FDS microdata can be obtained.

- Restricted access should also give access to narratives.

DATA BANK

Unfortunately, it was necessary to change the format of certain data records. Please make it possible to upload from now onward data sets as specified in annexes.

- An additional “Year” column had been added to the reference population files in order to avoid confusion. Please see annex 1 for the new data format. Please let us know, if we may forward the extended files to you in future.

- IDB-FDS data files: It was necessary to extend the lengths of the case-number (from 6 to 7 digits), the hospital provider-code (from 2 to 3 digits) and the narrative (from 120 to 200 digits). Please see annex 2 for the new IDB-FDS data format. Please let us know, if we may forward the extended files to you in future.

| Annex 1: Format of the IDB reference population data file (new format marked yellow) (For the codes for country and sex see the MDS Data Dictionary, in the Annex of the Manual) |  |  |  |
| --- | --- | --- | --- |
| Field | Number of characters | Position | Type of data |
| Year NEW!! | 4 | 1-4 | Numeric |
| Country | 2 | 5-6 | Numeric |
| Sex | 1 | 7 | Numeric |
| Age (in 1-year age groups) | 3 | 8-10 | Numeric |
| Number of persons of reference population | 10 | 11-20 | Numeric |

| Annex 2: Format for the IDB-FDS data file (new format marked yellow) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Data element | No. char. | Position start | Position end | Format | Type |
| Recording country | 2 | 1 | 2 | nn | Numeric |
| Unique national record number | 7 | 3 | 9 | nnnnnnn | Numeric |
| Age of patient | 3 | 10 | 12 | nnn | Numeric |
| Sex of patient | 1 | 13 | 13 | n | Numeric |
| Country of permanent residence | 2 | 14 | 15 | nn | Numeric |
| Date of injury | 8 | 16 | 23 | yyyymmdd | Date |
| Time of Injury | 2 | 24 | 25 | nn | Numeric |
| Date of attendance | 8 | 26 | 33 | yyyymmdd | Date |
| Time of attendance | 2 | 34 | 35 | nn | Numeric |
| Treatment and follow-up | 2 | 36 | 37 | nn | Numeric |
| Intent | 1 | 38 | 38 | n | Numeric |
| Transport injury event | 1 | 39 | 39 | n | Numeric |
| Place of occurrence | 5 | 40 | 44 | nn.nn | Numeric |
| Mechanism of injury | 5 | 45 | 49 | nn.nn | Numeric |
| Activity when injured | 4 | 50 | 53 | nn.n | Numeric |
| Underlying object/substance/product triggering the injury event | 7 | 54 | 60 | nn.nnnn | Numeric |
| Direct object/substance/product producing the injury | 7 | 61 | 67 | nn.nnnn | Numeric |
| Intermediate object/substance/product involved in another way | 7 | 68 | 74 | nn.nnnn | Numeric |
| Type 1 of injury | 2 | 75 | 76 | nn | Numeric |
| Type 2 of injury (if applicable) | 2 | 77 | 78 | nn | Numeric |
| Part 1 of the body injured | 4 | 79 | 82 | n.nn | Numeric |
| Part 2 of the body Injured (if applicable) | 4 | 83 | 86 | n.nn | Numeric |
| Narrative (optional) | 200 | 87 | 286 | 200n | Alphanumeric |
| Admission module (if applicable) |  |  |  |  |  |
| Number of days in hospital | 3 | 287 | 289 | nnn | Numeric |
| Violence module (if applicable) |  |  |  |  |  |
| Relation victim/perpetrator | 1 | 290 | 290 | n | Numeric |
| Sex of perpetrator | 1 | 291 | 291 | n | Numeric |
| Age of perpetrator | 1 | 292 | 292 | n | Numeric |
| Context of assault | 1 | 293 | 293 | n | Numeric |
| Intentional self-harm module (if applicable) |  |  |  |  |  |
| Proximal risk factor | 1 | 294 | 294 | n | Numeric |
| Previous intentional self-harm | 1 | 295 | 295 | n | Numeric |
| Transport module (if applicable) |  |  |  |  |  |
| Mode of transport | 4 | 296 | 299 | nn.n | Numeric |
| Role of injured person | 1 | 300 | 300 | n | Numeric |
| Counterpart | 4 | 301 | 304 | nn.n | Numeric |
| Sport module (if applicable) |  |  |  |  |  |
| Type of sport/exercise activity | 5 | 305 | 309 | nn.nn | Numeric |
| Provider (hospital) code (optional) | 3 | 310 | 312 | nnn | Numeric |
| Total record length | 312 | 1 | 312 |  |  |